## INT1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.094675 | 0.094995 | XGBoost | ensemble | INT1 | ARSI | Time
8 | 0.068507 | 0.094675 | 0.094995 | XGBoost | ensemble | INT1 | ARSI | Time
11 | 0.54806 | 0.44011 | 2.4871 | XGBoost | ensemble | INT1 | ARSI | Time
16 | 4.4494 | 7.2526 | 6.0323 | XGBoost | ensemble | INT1 | ARSI | Time
17 | 7.5598 | 9.5907 | 10.5865 | XGBoost | ensemble | INT1 | ARSI | Time
18 | 9.088 | 10.0805 | 10.5865 | XGBoost | ensemble | INT1 | ARSI | Time
21 | 15.0948 | 13.334 | 16.6898 | XGBoost | ensemble | INT1 | ARSI | Time
29 | 28.9617 | 29.9783 | 31.9 | XGBoost | ensemble | INT1 | ARSI | Time
32 | 31.2763 | 40.04 | 41.6215 | XGBoost | ensemble | INT1 | ARSI | Time
37 | 36.6192 | 46.287 | 47.8014 | XGBoost | ensemble | INT1 | ARSI | Time
42 | 45.2349 | 55.276 | 56.281 | XGBoost | ensemble | INT1 | ARSI | Time
55 | 74.2977 | 90.429 | 88.1755 | XGBoost | ensemble | INT1 | ARSI | Time
56 | 76.917 | 91.407 | 96.5523 | XGBoost | ensemble | INT1 | ARSI | Time
57 | 78.417 | 95.818 | 96.5523 | XGBoost | ensemble | INT1 | ARSI | Time
59 | 82.8509 | 96.504 | 97.8112 | XGBoost | ensemble | INT1 | ARSI | Time
76 | 100 | 99.732 | 99.7318 | XGBoost | ensemble | INT1 | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.094675 | 0.098092 | RandomForest | ensemble | INT1 | ARSI | Time
8 | 0.068507 | 0.094675 | 0.098092 | RandomForest | ensemble | INT1 | ARSI | Time
11 | 0.54806 | 0.44011 | 0.90887 | RandomForest | ensemble | INT1 | ARSI | Time
16 | 4.4494 | 7.2526 | 5.4387 | RandomForest | ensemble | INT1 | ARSI | Time
17 | 7.5598 | 9.5907 | 7.9921 | RandomForest | ensemble | INT1 | ARSI | Time
18 | 9.088 | 10.0805 | 10.0918 | RandomForest | ensemble | INT1 | ARSI | Time
21 | 15.0948 | 13.334 | 12.6019 | RandomForest | ensemble | INT1 | ARSI | Time
29 | 28.9617 | 29.9783 | 29.5589 | RandomForest | ensemble | INT1 | ARSI | Time
32 | 31.2763 | 40.04 | 36.3903 | RandomForest | ensemble | INT1 | ARSI | Time
37 | 36.6192 | 46.287 | 46.494 | RandomForest | ensemble | INT1 | ARSI | Time
42 | 45.2349 | 55.276 | 54.4343 | RandomForest | ensemble | INT1 | ARSI | Time
55 | 74.2977 | 90.429 | 87.8013 | RandomForest | ensemble | INT1 | ARSI | Time
56 | 76.917 | 91.407 | 92.1367 | RandomForest | ensemble | INT1 | ARSI | Time
57 | 78.417 | 95.818 | 94.9285 | RandomForest | ensemble | INT1 | ARSI | Time
59 | 82.8509 | 96.504 | 97.459 | RandomForest | ensemble | INT1 | ARSI | Time
76 | 100 | 99.732 | 99.7136 | RandomForest | ensemble | INT1 | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.094675 | -1.0126 | Blending | ensemble | INT1 | ARSI | Time
8 | 0.068507 | 0.094675 | -1.0488 | Blending | ensemble | INT1 | ARSI | Time
11 | 0.54806 | 0.44011 | 0.35621 | Blending | ensemble | INT1 | ARSI | Time
16 | 4.4494 | 7.2526 | 7.8938 | Blending | ensemble | INT1 | ARSI | Time
17 | 7.5598 | 9.5907 | 8.2483 | Blending | ensemble | INT1 | ARSI | Time
18 | 9.088 | 10.0805 | 9.8027 | Blending | ensemble | INT1 | ARSI | Time
21 | 15.0948 | 13.334 | 14.6731 | Blending | ensemble | INT1 | ARSI | Time
29 | 28.9617 | 29.9783 | 31.7512 | Blending | ensemble | INT1 | ARSI | Time
32 | 31.2763 | 40.04 | 37.6486 | Blending | ensemble | INT1 | ARSI | Time
37 | 36.6192 | 46.287 | 46.1135 | Blending | ensemble | INT1 | ARSI | Time
42 | 45.2349 | 55.276 | 56.9568 | Blending | ensemble | INT1 | ARSI | Time
55 | 74.2977 | 90.429 | 90.9504 | Blending | ensemble | INT1 | ARSI | Time
56 | 76.917 | 91.407 | 92.4962 | Blending | ensemble | INT1 | ARSI | Time
57 | 78.417 | 95.818 | 93.8355 | Blending | ensemble | INT1 | ARSI | Time
59 | 82.8509 | 96.504 | 96.0854 | Blending | ensemble | INT1 | ARSI | Time
76 | 100 | 99.732 | 99.2489 | Blending | ensemble | INT1 | ARSI | Time

## INT2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
6 | 0.33478 | 0.070992 | 0.071399 | XGBoost | ensemble | INT2 | ARSI | Time
7 | 0.53565 | 0.38291 | 4.04 | XGBoost | ensemble | INT2 | ARSI | Time
8 | 0.87043 | 2.6866 | 4.04 | XGBoost | ensemble | INT2 | ARSI | Time
10 | 1.7351 | 4.8757 | 4.04 | XGBoost | ensemble | INT2 | ARSI | Time
11 | 2.4324 | 6.0484 | 7.2508 | XGBoost | ensemble | INT2 | ARSI | Time
16 | 11.1298 | 13.4117 | 12.7572 | XGBoost | ensemble | INT2 | ARSI | Time
17 | 15.156 | 15.344 | 20.8593 | XGBoost | ensemble | INT2 | ARSI | Time
18 | 17.3714 | 19.6783 | 20.8593 | XGBoost | ensemble | INT2 | ARSI | Time
29 | 29.7066 | 37.6622 | 40.1762 | XGBoost | ensemble | INT2 | ARSI | Time
32 | 31.5827 | 44.4011 | 46.1549 | XGBoost | ensemble | INT2 | ARSI | Time
44 | 63.2648 | 60.4111 | 63.0578 | XGBoost | ensemble | INT2 | ARSI | Time
49 | 78.345 | 77.9133 | 79.0202 | XGBoost | ensemble | INT2 | ARSI | Time
51 | 82.8921 | 81.0622 | 82.5612 | XGBoost | ensemble | INT2 | ARSI | Time
56 | 91.1229 | 95.4911 | 96.2069 | XGBoost | ensemble | INT2 | ARSI | Time
72 | 100 | 99.29 | 99.6742 | XGBoost | ensemble | INT2 | ARSI | Time
74 | 100 | 99.6744 | 99.762 | XGBoost | ensemble | INT2 | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
6 | 0.33478 | 0.070992 | 0.11068 | RandomForest | ensemble | INT2 | ARSI | Time
7 | 0.53565 | 0.38291 | 0.38851 | RandomForest | ensemble | INT2 | ARSI | Time
8 | 0.87043 | 2.6866 | 2.8399 | RandomForest | ensemble | INT2 | ARSI | Time
10 | 1.7351 | 4.8757 | 4.2692 | RandomForest | ensemble | INT2 | ARSI | Time
11 | 2.4324 | 6.0484 | 6.5154 | RandomForest | ensemble | INT2 | ARSI | Time
16 | 11.1298 | 13.4117 | 12.1278 | RandomForest | ensemble | INT2 | ARSI | Time
17 | 15.156 | 15.344 | 17.7481 | RandomForest | ensemble | INT2 | ARSI | Time
18 | 17.3714 | 19.6783 | 21.3333 | RandomForest | ensemble | INT2 | ARSI | Time
29 | 29.7066 | 37.6622 | 35.0626 | RandomForest | ensemble | INT2 | ARSI | Time
32 | 31.5827 | 44.4011 | 43.5134 | RandomForest | ensemble | INT2 | ARSI | Time
44 | 63.2648 | 60.4111 | 61.2878 | RandomForest | ensemble | INT2 | ARSI | Time
49 | 78.345 | 77.9133 | 76.2931 | RandomForest | ensemble | INT2 | ARSI | Time
51 | 82.8921 | 81.0622 | 82.0211 | RandomForest | ensemble | INT2 | ARSI | Time
56 | 91.1229 | 95.4911 | 94.179 | RandomForest | ensemble | INT2 | ARSI | Time
72 | 100 | 99.29 | 99.3923 | RandomForest | ensemble | INT2 | ARSI | Time
74 | 100 | 99.6744 | 99.7164 | RandomForest | ensemble | INT2 | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
6 | 0.33478 | 0.070992 | -3.4612 | Blending | ensemble | INT2 | ARSI | Time
7 | 0.53565 | 0.38291 | -3.4079 | Blending | ensemble | INT2 | ARSI | Time
8 | 0.87043 | 2.6866 | -2.4963 | Blending | ensemble | INT2 | ARSI | Time
10 | 1.7351 | 4.8757 | 0.63537 | Blending | ensemble | INT2 | ARSI | Time
11 | 2.4324 | 6.0484 | 2.9669 | Blending | ensemble | INT2 | ARSI | Time
16 | 11.1298 | 13.4117 | 16.496 | Blending | ensemble | INT2 | ARSI | Time
17 | 15.156 | 15.344 | 18.8721 | Blending | ensemble | INT2 | ARSI | Time
18 | 17.3714 | 19.6783 | 20.046 | Blending | ensemble | INT2 | ARSI | Time
29 | 29.7066 | 37.6622 | 37.0203 | Blending | ensemble | INT2 | ARSI | Time
32 | 31.5827 | 44.4011 | 43.5261 | Blending | ensemble | INT2 | ARSI | Time
44 | 63.2648 | 60.4111 | 60.4182 | Blending | ensemble | INT2 | ARSI | Time
49 | 78.345 | 77.9133 | 80.4506 | Blending | ensemble | INT2 | ARSI | Time
51 | 82.8921 | 81.0622 | 87.8297 | Blending | ensemble | INT2 | ARSI | Time
56 | 91.1229 | 95.4911 | 94.9998 | Blending | ensemble | INT2 | ARSI | Time
72 | 100 | 99.29 | 100.8852 | Blending | ensemble | INT2 | ARSI | Time
74 | 100 | 99.6744 | 103.0024 | Blending | ensemble | INT2 | ARSI | Time

## EKS1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0 | 21.2217 | 13.7533 | XGBoost | ensemble | EKS1 | ARSI | Time
6 | 0 | 21.2217 | 21.2219 | XGBoost | ensemble | EKS1 | ARSI | Time
10 | 0 | 24.4919 | 21.2219 | XGBoost | ensemble | EKS1 | ARSI | Time
11 | 0 | 25.2904 | 25.2905 | XGBoost | ensemble | EKS1 | ARSI | Time
16 | 0 | 27.575 | 27.3446 | XGBoost | ensemble | EKS1 | ARSI | Time
17 | 0 | 33.9904 | 34.0743 | XGBoost | ensemble | EKS1 | ARSI | Time
44 | 34.0396 | 84.3 | 84.3001 | XGBoost | ensemble | EKS1 | ARSI | Time
46 | 43.9387 | 85.205 | 85.985 | XGBoost | ensemble | EKS1 | ARSI | Time
48 | 64.7904 | 86.115 | 86.1151 | XGBoost | ensemble | EKS1 | ARSI | Time
54 | 90.3836 | 86.195 | 86.63 | XGBoost | ensemble | EKS1 | ARSI | Time
62 | 100 | 99.9887 | 99.9885 | XGBoost | ensemble | EKS1 | ARSI | Time
65 | 100 | 99.9887 | 99.9885 | XGBoost | ensemble | EKS1 | ARSI | Time
66 | 100 | 99.9887 | 99.9885 | XGBoost | ensemble | EKS1 | ARSI | Time
68 | 100 | 99.9887 | 99.9885 | XGBoost | ensemble | EKS1 | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0 | 21.2217 | 13.7126 | RandomForest | ensemble | EKS1 | ARSI | Time
6 | 0 | 21.2217 | 19.5786 | RandomForest | ensemble | EKS1 | ARSI | Time
10 | 0 | 24.4919 | 21.5323 | RandomForest | ensemble | EKS1 | ARSI | Time
11 | 0 | 25.2904 | 24.5087 | RandomForest | ensemble | EKS1 | ARSI | Time
16 | 0 | 27.575 | 27.5455 | RandomForest | ensemble | EKS1 | ARSI | Time
17 | 0 | 33.9904 | 31.7174 | RandomForest | ensemble | EKS1 | ARSI | Time
44 | 34.0396 | 84.3 | 84.2863 | RandomForest | ensemble | EKS1 | ARSI | Time
46 | 43.9387 | 85.205 | 84.5708 | RandomForest | ensemble | EKS1 | ARSI | Time
48 | 64.7904 | 86.115 | 86.0663 | RandomForest | ensemble | EKS1 | ARSI | Time
54 | 90.3836 | 86.195 | 86.3146 | RandomForest | ensemble | EKS1 | ARSI | Time
62 | 100 | 99.9887 | 99.9887 | RandomForest | ensemble | EKS1 | ARSI | Time
65 | 100 | 99.9887 | 99.9887 | RandomForest | ensemble | EKS1 | ARSI | Time
66 | 100 | 99.9887 | 99.9889 | RandomForest | ensemble | EKS1 | ARSI | Time
68 | 100 | 99.9887 | 99.9897 | RandomForest | ensemble | EKS1 | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0 | 21.2217 | 15.1345 | Blending | ensemble | EKS1 | ARSI | Time
6 | 0 | 21.2217 | 16.708 | Blending | ensemble | EKS1 | ARSI | Time
10 | 0 | 24.4919 | 22.2087 | Blending | ensemble | EKS1 | ARSI | Time
11 | 0 | 25.2904 | 23.4671 | Blending | ensemble | EKS1 | ARSI | Time
16 | 0 | 27.575 | 29.649 | Blending | ensemble | EKS1 | ARSI | Time
17 | 0 | 33.9904 | 30.9144 | Blending | ensemble | EKS1 | ARSI | Time
44 | 34.0396 | 84.3 | 89.7415 | Blending | ensemble | EKS1 | ARSI | Time
46 | 43.9387 | 85.205 | 90.3912 | Blending | ensemble | EKS1 | ARSI | Time
48 | 64.7904 | 86.115 | 84.8774 | Blending | ensemble | EKS1 | ARSI | Time
54 | 90.3836 | 86.195 | 87.379 | Blending | ensemble | EKS1 | ARSI | Time
62 | 100 | 99.9887 | 97.0189 | Blending | ensemble | EKS1 | ARSI | Time
65 | 100 | 99.9887 | 103.9655 | Blending | ensemble | EKS1 | ARSI | Time
66 | 100 | 99.9887 | 106.4484 | Blending | ensemble | EKS1 | ARSI | Time
68 | 100 | 99.9887 | 111.6439 | Blending | ensemble | EKS1 | ARSI | Time

## EKS2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0 | 20.5594 | 13.8257 | XGBoost | ensemble | EKS2 | ARSI | Time
6 | 0 | 21.2878 | 21.288 | XGBoost | ensemble | EKS2 | ARSI | Time
8 | 0 | 21.2878 | 21.288 | XGBoost | ensemble | EKS2 | ARSI | Time
11 | 0 | 25.3529 | 25.3505 | XGBoost | ensemble | EKS2 | ARSI | Time
17 | 0 | 33.1317 | 33.2987 | XGBoost | ensemble | EKS2 | ARSI | Time
19 | 0 | 33.2986 | 33.3002 | XGBoost | ensemble | EKS2 | ARSI | Time
25 | 0 | 41.675 | 42.5548 | XGBoost | ensemble | EKS2 | ARSI | Time
40 | 21.7449 | 49.655 | 49.6557 | XGBoost | ensemble | EKS2 | ARSI | Time
42 | 30.5459 | 89.675 | 90.715 | XGBoost | ensemble | EKS2 | ARSI | Time
48 | 57.8202 | 97.865 | 97.8641 | XGBoost | ensemble | EKS2 | ARSI | Time
55 | 89.5352 | 99.725 | 99.725 | XGBoost | ensemble | EKS2 | ARSI | Time
58 | 100 | 99.725 | 99.725 | XGBoost | ensemble | EKS2 | ARSI | Time
59 | 100 | 99.725 | 99.7348 | XGBoost | ensemble | EKS2 | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0 | 20.5594 | 13.6835 | RandomForest | ensemble | EKS2 | ARSI | Time
6 | 0 | 21.2878 | 18.5922 | RandomForest | ensemble | EKS2 | ARSI | Time
8 | 0 | 21.2878 | 21.1236 | RandomForest | ensemble | EKS2 | ARSI | Time
11 | 0 | 25.3529 | 23.4957 | RandomForest | ensemble | EKS2 | ARSI | Time
17 | 0 | 33.1317 | 29.0857 | RandomForest | ensemble | EKS2 | ARSI | Time
19 | 0 | 33.2986 | 33.6452 | RandomForest | ensemble | EKS2 | ARSI | Time
25 | 0 | 41.675 | 41.3058 | RandomForest | ensemble | EKS2 | ARSI | Time
40 | 21.7449 | 49.655 | 49.3758 | RandomForest | ensemble | EKS2 | ARSI | Time
42 | 30.5459 | 89.675 | 60.9295 | RandomForest | ensemble | EKS2 | ARSI | Time
48 | 57.8202 | 97.865 | 95.6325 | RandomForest | ensemble | EKS2 | ARSI | Time
55 | 89.5352 | 99.725 | 99.6812 | RandomForest | ensemble | EKS2 | ARSI | Time
58 | 100 | 99.725 | 99.7285 | RandomForest | ensemble | EKS2 | ARSI | Time
59 | 100 | 99.725 | 99.7352 | RandomForest | ensemble | EKS2 | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0 | 20.5594 | 13.597 | Blending | ensemble | EKS2 | ARSI | Time
6 | 0 | 21.2878 | 14.5672 | Blending | ensemble | EKS2 | ARSI | Time
8 | 0 | 21.2878 | 16.9988 | Blending | ensemble | EKS2 | ARSI | Time
11 | 0 | 25.3529 | 21.1464 | Blending | ensemble | EKS2 | ARSI | Time
17 | 0 | 33.1317 | 29.3402 | Blending | ensemble | EKS2 | ARSI | Time
19 | 0 | 33.2986 | 32.0382 | Blending | ensemble | EKS2 | ARSI | Time
25 | 0 | 41.675 | 40.3115 | Blending | ensemble | EKS2 | ARSI | Time
40 | 21.7449 | 49.655 | 43.8921 | Blending | ensemble | EKS2 | ARSI | Time
42 | 30.5459 | 89.675 | 60.8643 | Blending | ensemble | EKS2 | ARSI | Time
48 | 57.8202 | 97.865 | 94.3085 | Blending | ensemble | EKS2 | ARSI | Time
55 | 89.5352 | 99.725 | 104.8673 | Blending | ensemble | EKS2 | ARSI | Time
58 | 100 | 99.725 | 95.4648 | Blending | ensemble | EKS2 | ARSI | Time
59 | 100 | 99.725 | 85.9188 | Blending | ensemble | EKS2 | ARSI | Time

## GKB1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.078896 | 0.079205 | XGBoost | ensemble | GKB1 | ARSI | Time
8 | 0.052859 | 0.078896 | 0.079205 | XGBoost | ensemble | GKB1 | ARSI | Time
11 | 0.42287 | 1.2652 | 2.9711 | XGBoost | ensemble | GKB1 | ARSI | Time
16 | 3.433 | 9.5808 | 8.5639 | XGBoost | ensemble | GKB1 | ARSI | Time
17 | 5.833 | 11.5292 | 12.3591 | XGBoost | ensemble | GKB1 | ARSI | Time
18 | 7.0121 | 11.9374 | 12.3591 | XGBoost | ensemble | GKB1 | ARSI | Time
21 | 11.6468 | 15.3268 | 18.1234 | XGBoost | ensemble | GKB1 | ARSI | Time
29 | 22.3462 | 30.661 | 32.2603 | XGBoost | ensemble | GKB1 | ARSI | Time
32 | 24.1321 | 40.3417 | 41.6839 | XGBoost | ensemble | GKB1 | ARSI | Time
37 | 28.2545 | 46.0867 | 47.4458 | XGBoost | ensemble | GKB1 | ARSI | Time
42 | 34.9023 | 54.1225 | 54.9594 | XGBoost | ensemble | GKB1 | ARSI | Time
55 | 65.8087 | 89.4075 | 87.5309 | XGBoost | ensemble | GKB1 | ARSI | Time
56 | 69.384 | 90.3733 | 94.8143 | XGBoost | ensemble | GKB1 | ARSI | Time
57 | 74.3393 | 94.1792 | 94.8143 | XGBoost | ensemble | GKB1 | ARSI | Time
59 | 79.6238 | 94.7725 | 95.8664 | XGBoost | ensemble | GKB1 | ARSI | Time
76 | 100 | 99.7748 | 99.7746 | XGBoost | ensemble | GKB1 | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.078896 | 0.078896 | RandomForest | ensemble | GKB1 | ARSI | Time
8 | 0.052859 | 0.078896 | 0.078896 | RandomForest | ensemble | GKB1 | ARSI | Time
11 | 0.42287 | 1.2652 | 0.97135 | RandomForest | ensemble | GKB1 | ARSI | Time
16 | 3.433 | 9.5808 | 7.1315 | RandomForest | ensemble | GKB1 | ARSI | Time
17 | 5.833 | 11.5292 | 9.8866 | RandomForest | ensemble | GKB1 | ARSI | Time
18 | 7.0121 | 11.9374 | 12.0397 | RandomForest | ensemble | GKB1 | ARSI | Time
21 | 11.6468 | 15.3268 | 14.53 | RandomForest | ensemble | GKB1 | ARSI | Time
29 | 22.3462 | 30.661 | 29.9763 | RandomForest | ensemble | GKB1 | ARSI | Time
32 | 24.1321 | 40.3417 | 36.2738 | RandomForest | ensemble | GKB1 | ARSI | Time
37 | 28.2545 | 46.0867 | 46.2106 | RandomForest | ensemble | GKB1 | ARSI | Time
42 | 34.9023 | 54.1225 | 53.3681 | RandomForest | ensemble | GKB1 | ARSI | Time
55 | 65.8087 | 89.4075 | 86.6452 | RandomForest | ensemble | GKB1 | ARSI | Time
56 | 69.384 | 90.3733 | 88.7046 | RandomForest | ensemble | GKB1 | ARSI | Time
57 | 74.3393 | 94.1792 | 93.9854 | RandomForest | ensemble | GKB1 | ARSI | Time
59 | 79.6238 | 94.7725 | 95.4985 | RandomForest | ensemble | GKB1 | ARSI | Time
76 | 100 | 99.7748 | 99.7704 | RandomForest | ensemble | GKB1 | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.078896 | 0.27044 | Blending | ensemble | GKB1 | ARSI | Time
8 | 0.052859 | 0.078896 | 0.93689 | Blending | ensemble | GKB1 | ARSI | Time
11 | 0.42287 | 1.2652 | 3.7184 | Blending | ensemble | GKB1 | ARSI | Time
16 | 3.433 | 9.5808 | 10.2537 | Blending | ensemble | GKB1 | ARSI | Time
17 | 5.833 | 11.5292 | 12.0276 | Blending | ensemble | GKB1 | ARSI | Time
18 | 7.0121 | 11.9374 | 13.5564 | Blending | ensemble | GKB1 | ARSI | Time
21 | 11.6468 | 15.3268 | 18.4942 | Blending | ensemble | GKB1 | ARSI | Time
29 | 22.3462 | 30.661 | 32.2138 | Blending | ensemble | GKB1 | ARSI | Time
32 | 24.1321 | 40.3417 | 37.0751 | Blending | ensemble | GKB1 | ARSI | Time
37 | 28.2545 | 46.0867 | 45.2577 | Blending | ensemble | GKB1 | ARSI | Time
42 | 34.9023 | 54.1225 | 54.7304 | Blending | ensemble | GKB1 | ARSI | Time
55 | 65.8087 | 89.4075 | 90.3063 | Blending | ensemble | GKB1 | ARSI | Time
56 | 69.384 | 90.3733 | 92.0073 | Blending | ensemble | GKB1 | ARSI | Time
57 | 74.3393 | 94.1792 | 93.0632 | Blending | ensemble | GKB1 | ARSI | Time
59 | 79.6238 | 94.7725 | 94.9846 | Blending | ensemble | GKB1 | ARSI | Time
76 | 100 | 99.7748 | 99.7035 | Blending | ensemble | GKB1 | ARSI | Time

## GKB2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
6 | 0.26001 | 0.058084 | 0.058471 | XGBoost | ensemble | GKB2 | ARSI | Time
7 | 0.41601 | 1.2905 | 5.4242 | XGBoost | ensemble | GKB2 | ARSI | Time
8 | 0.67602 | 3.1753 | 5.4242 | XGBoost | ensemble | GKB2 | ARSI | Time
10 | 1.3476 | 6.5029 | 5.4242 | XGBoost | ensemble | GKB2 | ARSI | Time
11 | 1.8891 | 8.6867 | 9.803 | XGBoost | ensemble | GKB2 | ARSI | Time
16 | 8.6439 | 15.1691 | 14.3086 | XGBoost | ensemble | GKB2 | ARSI | Time
17 | 11.7709 | 17.1638 | 21.9906 | XGBoost | ensemble | GKB2 | ARSI | Time
18 | 13.4915 | 20.71 | 21.9906 | XGBoost | ensemble | GKB2 | ARSI | Time
29 | 23.0716 | 37.9091 | 40.366 | XGBoost | ensemble | GKB2 | ARSI | Time
32 | 24.5287 | 44.0655 | 45.5845 | XGBoost | ensemble | GKB2 | ARSI | Time
44 | 52.6037 | 58.0574 | 60.6221 | XGBoost | ensemble | GKB2 | ARSI | Time
49 | 69.4022 | 80.2409 | 81.1455 | XGBoost | ensemble | GKB2 | ARSI | Time
51 | 74.8994 | 83.1055 | 84.4362 | XGBoost | ensemble | GKB2 | ARSI | Time
56 | 85.5992 | 96.0036 | 96.6679 | XGBoost | ensemble | GKB2 | ARSI | Time
72 | 100 | 99.4191 | 99.7334 | XGBoost | ensemble | GKB2 | ARSI | Time
74 | 100 | 99.7336 | 99.8052 | XGBoost | ensemble | GKB2 | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
6 | 0.26001 | 0.058084 | 0.45513 | RandomForest | ensemble | GKB2 | ARSI | Time
7 | 0.41601 | 1.2905 | 0.87826 | RandomForest | ensemble | GKB2 | ARSI | Time
8 | 0.67602 | 3.1753 | 3.2772 | RandomForest | ensemble | GKB2 | ARSI | Time
10 | 1.3476 | 6.5029 | 4.9533 | RandomForest | ensemble | GKB2 | ARSI | Time
11 | 1.8891 | 8.6867 | 8.8535 | RandomForest | ensemble | GKB2 | ARSI | Time
16 | 8.6439 | 15.1691 | 13.4822 | RandomForest | ensemble | GKB2 | ARSI | Time
17 | 11.7709 | 17.1638 | 18.5712 | RandomForest | ensemble | GKB2 | ARSI | Time
18 | 13.4915 | 20.71 | 22.5492 | RandomForest | ensemble | GKB2 | ARSI | Time
29 | 23.0716 | 37.9091 | 36.5499 | RandomForest | ensemble | GKB2 | ARSI | Time
32 | 24.5287 | 44.0655 | 42.6662 | RandomForest | ensemble | GKB2 | ARSI | Time
44 | 52.6037 | 58.0574 | 58.8399 | RandomForest | ensemble | GKB2 | ARSI | Time
49 | 69.4022 | 80.2409 | 78.2064 | RandomForest | ensemble | GKB2 | ARSI | Time
51 | 74.8994 | 83.1055 | 83.4503 | RandomForest | ensemble | GKB2 | ARSI | Time
56 | 85.5992 | 96.0036 | 94.7369 | RandomForest | ensemble | GKB2 | ARSI | Time
72 | 100 | 99.4191 | 99.517 | RandomForest | ensemble | GKB2 | ARSI | Time
74 | 100 | 99.7336 | 99.6308 | RandomForest | ensemble | GKB2 | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
6 | 0.26001 | 0.058084 | 3.123 | Blending | ensemble | GKB2 | ARSI | Time
7 | 0.41601 | 1.2905 | 4.8334 | Blending | ensemble | GKB2 | ARSI | Time
8 | 0.67602 | 3.1753 | 6.7347 | Blending | ensemble | GKB2 | ARSI | Time
10 | 1.3476 | 6.5029 | 10.952 | Blending | ensemble | GKB2 | ARSI | Time
11 | 1.8891 | 8.6867 | 13.0217 | Blending | ensemble | GKB2 | ARSI | Time
16 | 8.6439 | 15.1691 | 18.8598 | Blending | ensemble | GKB2 | ARSI | Time
17 | 11.7709 | 17.1638 | 18.6968 | Blending | ensemble | GKB2 | ARSI | Time
18 | 13.4915 | 20.71 | 19.7938 | Blending | ensemble | GKB2 | ARSI | Time
29 | 23.0716 | 37.9091 | 37.8882 | Blending | ensemble | GKB2 | ARSI | Time
32 | 24.5287 | 44.0655 | 44.4471 | Blending | ensemble | GKB2 | ARSI | Time
44 | 52.6037 | 58.0574 | 58.6599 | Blending | ensemble | GKB2 | ARSI | Time
49 | 69.4022 | 80.2409 | 80.0898 | Blending | ensemble | GKB2 | ARSI | Time
51 | 74.8994 | 83.1055 | 87.1451 | Blending | ensemble | GKB2 | ARSI | Time
56 | 85.5992 | 96.0036 | 96.5292 | Blending | ensemble | GKB2 | ARSI | Time
72 | 100 | 99.4191 | 101.7361 | Blending | ensemble | GKB2 | ARSI | Time
74 | 100 | 99.7336 | 103.3918 | Blending | ensemble | GKB2 | ARSI | Time

## KUM
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.06849 | 0.06863 | XGBoost | ensemble | KUM | ARSI | Time
8 | 0.052425 | 0.06849 | 0.06863 | XGBoost | ensemble | KUM | ARSI | Time
11 | 0.4194 | 1.2778 | 3.0732 | XGBoost | ensemble | KUM | ARSI | Time
16 | 3.0411 | 9.6919 | 8.6253 | XGBoost | ensemble | KUM | ARSI | Time
17 | 4.6714 | 11.5964 | 13.3338 | XGBoost | ensemble | KUM | ARSI | Time
18 | 6.0703 | 12.7413 | 13.3338 | XGBoost | ensemble | KUM | ARSI | Time
21 | 11.7096 | 16.2453 | 19.4167 | XGBoost | ensemble | KUM | ARSI | Time
29 | 22.095 | 30.1763 | 31.0534 | XGBoost | ensemble | KUM | ARSI | Time
32 | 23.4174 | 37.5063 | 39.798 | XGBoost | ensemble | KUM | ARSI | Time
37 | 26.7029 | 45.8365 | 46.8151 | XGBoost | ensemble | KUM | ARSI | Time
42 | 35.2066 | 52.3272 | 53.0225 | XGBoost | ensemble | KUM | ARSI | Time
55 | 70.4062 | 86.2565 | 84.34 | XGBoost | ensemble | KUM | ARSI | Time
56 | 73.0492 | 87.4039 | 94.6291 | XGBoost | ensemble | KUM | ARSI | Time
57 | 76.4125 | 92.8314 | 94.6291 | XGBoost | ensemble | KUM | ARSI | Time
59 | 81.537 | 94.4222 | 95.938 | XGBoost | ensemble | KUM | ARSI | Time
76 | 100 | 99.5969 | 99.754 | XGBoost | ensemble | KUM | ARSI | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.06849 | 0.065586 | RandomForest | ensemble | KUM | ARSI | Time
8 | 0.052425 | 0.06849 | 0.066166 | RandomForest | ensemble | KUM | ARSI | Time
11 | 0.4194 | 1.2778 | 0.71407 | RandomForest | ensemble | KUM | ARSI | Time
16 | 3.0411 | 9.6919 | 7.8333 | RandomForest | ensemble | KUM | ARSI | Time
17 | 4.6714 | 11.5964 | 9.8459 | RandomForest | ensemble | KUM | ARSI | Time
18 | 6.0703 | 12.7413 | 13.1054 | RandomForest | ensemble | KUM | ARSI | Time
21 | 11.7096 | 16.2453 | 15.6931 | RandomForest | ensemble | KUM | ARSI | Time
29 | 22.095 | 30.1763 | 29.5899 | RandomForest | ensemble | KUM | ARSI | Time
32 | 23.4174 | 37.5063 | 36.1334 | RandomForest | ensemble | KUM | ARSI | Time
37 | 26.7029 | 45.8365 | 45.253 | RandomForest | ensemble | KUM | ARSI | Time
42 | 35.2066 | 52.3272 | 51.4014 | RandomForest | ensemble | KUM | ARSI | Time
55 | 70.4062 | 86.2565 | 84.4139 | RandomForest | ensemble | KUM | ARSI | Time
56 | 73.0492 | 87.4039 | 86.1322 | RandomForest | ensemble | KUM | ARSI | Time
57 | 76.4125 | 92.8314 | 91.8797 | RandomForest | ensemble | KUM | ARSI | Time
59 | 81.537 | 94.4222 | 95.321 | RandomForest | ensemble | KUM | ARSI | Time
76 | 100 | 99.5969 | 99.627 | RandomForest | ensemble | KUM | ARSI | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
7 | 0 | 0.06849 | -2.5412 | Blending | ensemble | KUM | ARSI | Time
8 | 0.052425 | 0.06849 | -2.7803 | Blending | ensemble | KUM | ARSI | Time
11 | 0.4194 | 1.2778 | -0.43917 | Blending | ensemble | KUM | ARSI | Time
16 | 3.0411 | 9.6919 | 10.7461 | Blending | ensemble | KUM | ARSI | Time
17 | 4.6714 | 11.5964 | 11.3091 | Blending | ensemble | KUM | ARSI | Time
18 | 6.0703 | 12.7413 | 12.5366 | Blending | ensemble | KUM | ARSI | Time
21 | 11.7096 | 16.2453 | 15.4435 | Blending | ensemble | KUM | ARSI | Time
29 | 22.095 | 30.1763 | 30.683 | Blending | ensemble | KUM | ARSI | Time
32 | 23.4174 | 37.5063 | 36.8083 | Blending | ensemble | KUM | ARSI | Time
37 | 26.7029 | 45.8365 | 46.0531 | Blending | ensemble | KUM | ARSI | Time
42 | 35.2066 | 52.3272 | 49.4342 | Blending | ensemble | KUM | ARSI | Time
55 | 70.4062 | 86.2565 | 89.5775 | Blending | ensemble | KUM | ARSI | Time
56 | 73.0492 | 87.4039 | 91.6385 | Blending | ensemble | KUM | ARSI | Time
57 | 76.4125 | 92.8314 | 93.9555 | Blending | ensemble | KUM | ARSI | Time
59 | 81.537 | 94.4222 | 95.7416 | Blending | ensemble | KUM | ARSI | Time
76 | 100 | 99.5969 | 99.7061 | Blending | ensemble | KUM | ARSI | Time