## K1B1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
9 | 14.1545 | 90.3938 | 97.7889 | XGBoost | ensemble | K1B1 | KONS | Time
12 | 26.2345 | 98.8045 | 98.8047 | XGBoost | ensemble | K1B1 | KONS | Time
17 | 40.8005 | 98.8045 | 98.9349 | XGBoost | ensemble | K1B1 | KONS | Time
19 | 49.7817 | 98.9419 | 98.9349 | XGBoost | ensemble | K1B1 | KONS | Time
20 | 56.592 | 98.9419 | 98.9408 | XGBoost | ensemble | K1B1 | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
9 | 14.1545 | 90.3938 | 89.9911 | RandomForest | ensemble | K1B1 | KONS | Time
12 | 26.2345 | 98.8045 | 98.2901 | RandomForest | ensemble | K1B1 | KONS | Time
17 | 40.8005 | 98.8045 | 98.8786 | RandomForest | ensemble | K1B1 | KONS | Time
19 | 49.7817 | 98.9419 | 98.8877 | RandomForest | ensemble | K1B1 | KONS | Time
20 | 56.592 | 98.9419 | 98.9 | RandomForest | ensemble | K1B1 | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
9 | 14.1545 | 90.3938 | 68.2207 | Blending | ensemble | K1B1 | KONS | Time
12 | 26.2345 | 98.8045 | 83.1089 | Blending | ensemble | K1B1 | KONS | Time
17 | 40.8005 | 98.8045 | 125.327 | Blending | ensemble | K1B1 | KONS | Time
19 | 49.7817 | 98.9419 | 78.6308 | Blending | ensemble | K1B1 | KONS | Time
20 | 56.592 | 98.9419 | 110.9653 | Blending | ensemble | K1B1 | KONS | Time

## K1B2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
9 | 13.2377 | 96.1803 | 97.9679 | XGBoost | ensemble | K1B2 | KONS | Time
12 | 21.2534 | 98.4564 | 98.4568 | XGBoost | ensemble | K1B2 | KONS | Time
14 | 26.5973 | 98.5594 | 98.559 | XGBoost | ensemble | K1B2 | KONS | Time
17 | 33.3329 | 99.0839 | 99.0825 | XGBoost | ensemble | K1B2 | KONS | Time
19 | 41.6229 | 99.2504 | 99.0825 | XGBoost | ensemble | K1B2 | KONS | Time
20 | 50.9491 | 99.25 | 99.6113 | XGBoost | ensemble | K1B2 | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
9 | 13.2377 | 96.1803 | 92.9266 | RandomForest | ensemble | K1B2 | KONS | Time
12 | 21.2534 | 98.4564 | 98.4338 | RandomForest | ensemble | K1B2 | KONS | Time
14 | 26.5973 | 98.5594 | 98.5055 | RandomForest | ensemble | K1B2 | KONS | Time
17 | 33.3329 | 99.0839 | 98.9222 | RandomForest | ensemble | K1B2 | KONS | Time
19 | 41.6229 | 99.2504 | 99.1354 | RandomForest | ensemble | K1B2 | KONS | Time
20 | 50.9491 | 99.25 | 99.5452 | RandomForest | ensemble | K1B2 | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
9 | 13.2377 | 96.1803 | 79.8358 | Blending | ensemble | K1B2 | KONS | Time
12 | 21.2534 | 98.4564 | 89.4548 | Blending | ensemble | K1B2 | KONS | Time
14 | 26.5973 | 98.5594 | 111.6982 | Blending | ensemble | K1B2 | KONS | Time
17 | 33.3329 | 99.0839 | 209.5437 | Blending | ensemble | K1B2 | KONS | Time
19 | 41.6229 | 99.2504 | 231.9436 | Blending | ensemble | K1B2 | KONS | Time
20 | 50.9491 | 99.25 | 148.9658 | Blending | ensemble | K1B2 | KONS | Time

## K2B1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
2 | 3.7509 | 0.28911 | 2.0037 | XGBoost | ensemble | K2B1 | KONS | Time
5 | 16.7589 | 6.8287 | 4.6746 | XGBoost | ensemble | K2B1 | KONS | Time
6 | 22.7347 | 12.2706 | 14.7121 | XGBoost | ensemble | K2B1 | KONS | Time
10 | 33.6587 | 18.2341 | 16.9653 | XGBoost | ensemble | K2B1 | KONS | Time
11 | 39.1355 | 19.9577 | 21.1882 | XGBoost | ensemble | K2B1 | KONS | Time
19 | 73.6851 | 46.75 | 41.2915 | XGBoost | ensemble | K2B1 | KONS | Time
20 | 79.8691 | 53.278 | 56.6905 | XGBoost | ensemble | K2B1 | KONS | Time
23 | 93.836 | 65.153 | 70.8269 | XGBoost | ensemble | K2B1 | KONS | Time
28 | 100 | 86.61 | 90.0073 | XGBoost | ensemble | K2B1 | KONS | Time
30 | 100 | 91.372 | 91.6541 | XGBoost | ensemble | K2B1 | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
2 | 3.7509 | 0.28911 | 2.3363 | RandomForest | ensemble | K2B1 | KONS | Time
5 | 16.7589 | 6.8287 | 5.6279 | RandomForest | ensemble | K2B1 | KONS | Time
6 | 22.7347 | 12.2706 | 13.5147 | RandomForest | ensemble | K2B1 | KONS | Time
10 | 33.6587 | 18.2341 | 16.6537 | RandomForest | ensemble | K2B1 | KONS | Time
11 | 39.1355 | 19.9577 | 20.7264 | RandomForest | ensemble | K2B1 | KONS | Time
19 | 73.6851 | 46.75 | 41.6548 | RandomForest | ensemble | K2B1 | KONS | Time
20 | 79.8691 | 53.278 | 53.7448 | RandomForest | ensemble | K2B1 | KONS | Time
23 | 93.836 | 65.153 | 64.0828 | RandomForest | ensemble | K2B1 | KONS | Time
28 | 100 | 86.61 | 85.5544 | RandomForest | ensemble | K2B1 | KONS | Time
30 | 100 | 91.372 | 90.7408 | RandomForest | ensemble | K2B1 | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
2 | 3.7509 | 0.28911 | 14.6339 | Blending | ensemble | K2B1 | KONS | Time
5 | 16.7589 | 6.8287 | 7.5416 | Blending | ensemble | K2B1 | KONS | Time
6 | 22.7347 | 12.2706 | 11.7702 | Blending | ensemble | K2B1 | KONS | Time
10 | 33.6587 | 18.2341 | -4.1099 | Blending | ensemble | K2B1 | KONS | Time
11 | 39.1355 | 19.9577 | 4.9342 | Blending | ensemble | K2B1 | KONS | Time
19 | 73.6851 | 46.75 | 64.6956 | Blending | ensemble | K2B1 | KONS | Time
20 | 79.8691 | 53.278 | 70.5248 | Blending | ensemble | K2B1 | KONS | Time
23 | 93.836 | 65.153 | 76.4415 | Blending | ensemble | K2B1 | KONS | Time
28 | 100 | 86.61 | 87.6081 | Blending | ensemble | K2B1 | KONS | Time
30 | 100 | 91.372 | 90.8222 | Blending | ensemble | K2B1 | KONS | Time

## K2B2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 12.9382 | 12.2696 | 8.1119 | XGBoost | ensemble | K2B2 | KONS | Time
6 | 18.2978 | 13.3613 | 14.4353 | XGBoost | ensemble | K2B2 | KONS | Time
10 | 29.6089 | 18.2978 | 17.0132 | XGBoost | ensemble | K2B2 | KONS | Time
11 | 32.7135 | 19.1572 | 22.6236 | XGBoost | ensemble | K2B2 | KONS | Time
17 | 57.7072 | 49.3433 | 57.329 | XGBoost | ensemble | K2B2 | KONS | Time
19 | 74.5568 | 59.9744 | 62.3013 | XGBoost | ensemble | K2B2 | KONS | Time
23 | 95.3734 | 77.2244 | 80.9973 | XGBoost | ensemble | K2B2 | KONS | Time
42 | 100 | 99.9856 | 99.9855 | XGBoost | ensemble | K2B2 | KONS | Time
48 | 100 | 99.9856 | 99.9855 | XGBoost | ensemble | K2B2 | KONS | Time
49 | 100 | 99.9856 | 99.9987 | XGBoost | ensemble | K2B2 | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 12.9382 | 12.2696 | 7.7732 | RandomForest | ensemble | K2B2 | KONS | Time
6 | 18.2978 | 13.3613 | 13.6943 | RandomForest | ensemble | K2B2 | KONS | Time
10 | 29.6089 | 18.2978 | 17.0726 | RandomForest | ensemble | K2B2 | KONS | Time
11 | 32.7135 | 19.1572 | 21.8418 | RandomForest | ensemble | K2B2 | KONS | Time
17 | 57.7072 | 49.3433 | 44.8566 | RandomForest | ensemble | K2B2 | KONS | Time
19 | 74.5568 | 59.9744 | 60.5566 | RandomForest | ensemble | K2B2 | KONS | Time
23 | 95.3734 | 77.2244 | 76.2209 | RandomForest | ensemble | K2B2 | KONS | Time
42 | 100 | 99.9856 | 99.9665 | RandomForest | ensemble | K2B2 | KONS | Time
48 | 100 | 99.9856 | 99.9665 | RandomForest | ensemble | K2B2 | KONS | Time
49 | 100 | 99.9856 | 99.9666 | RandomForest | ensemble | K2B2 | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 12.9382 | 12.2696 | 12.6776 | Blending | ensemble | K2B2 | KONS | Time
6 | 18.2978 | 13.3613 | 17.8433 | Blending | ensemble | K2B2 | KONS | Time
10 | 29.6089 | 18.2978 | 33.5732 | Blending | ensemble | K2B2 | KONS | Time
11 | 32.7135 | 19.1572 | 37.9488 | Blending | ensemble | K2B2 | KONS | Time
17 | 57.7072 | 49.3433 | 67.6543 | Blending | ensemble | K2B2 | KONS | Time
19 | 74.5568 | 59.9744 | 74.7427 | Blending | ensemble | K2B2 | KONS | Time
23 | 95.3734 | 77.2244 | 80.2057 | Blending | ensemble | K2B2 | KONS | Time
42 | 100 | 99.9856 | 99.942 | Blending | ensemble | K2B2 | KONS | Time
48 | 100 | 99.9856 | 99.8554 | Blending | ensemble | K2B2 | KONS | Time
49 | 100 | 99.9856 | 99.939 | Blending | ensemble | K2B2 | KONS | Time

## K3B1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
8 | 100 | 82.9083 | 82.9092 | XGBoost | ensemble | K3B1 | KONS | Time
10 | 100 | 82.9083 | 82.965 | XGBoost | ensemble | K3B1 | KONS | Time
12 | 100 | 82.9674 | 83.8644 | XGBoost | ensemble | K3B1 | KONS | Time
17 | 100 | 93.812 | 92.1761 | XGBoost | ensemble | K3B1 | KONS | Time
18 | 100 | 98.4085 | 99.6805 | XGBoost | ensemble | K3B1 | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
8 | 100 | 82.9083 | 82.9535 | RandomForest | ensemble | K3B1 | KONS | Time
10 | 100 | 82.9083 | 83.1557 | RandomForest | ensemble | K3B1 | KONS | Time
12 | 100 | 82.9674 | 83.6216 | RandomForest | ensemble | K3B1 | KONS | Time
17 | 100 | 93.812 | 91.9445 | RandomForest | ensemble | K3B1 | KONS | Time
18 | 100 | 98.4085 | 97.7451 | RandomForest | ensemble | K3B1 | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
8 | 100 | 82.9083 | 83.2054 | Blending | ensemble | K3B1 | KONS | Time
10 | 100 | 82.9083 | 83.0024 | Blending | ensemble | K3B1 | KONS | Time
12 | 100 | 82.9674 | 84.3204 | Blending | ensemble | K3B1 | KONS | Time
17 | 100 | 93.812 | 93.7081 | Blending | ensemble | K3B1 | KONS | Time
18 | 100 | 98.4085 | 96.5464 | Blending | ensemble | K3B1 | KONS | Time

## K3B2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
8 | 100 | 30.978 | 36.8684 | XGBoost | ensemble | K3B2 | KONS | Time
12 | 100 | 74.4384 | 81.0733 | XGBoost | ensemble | K3B2 | KONS | Time
14 | 100 | 82.8772 | 85.0654 | XGBoost | ensemble | K3B2 | KONS | Time
17 | 100 | 85.7422 | 85.7425 | XGBoost | ensemble | K3B2 | KONS | Time
20 | 100 | 91.5303 | 94.2462 | XGBoost | ensemble | K3B2 | KONS | Time
25 | 100 | 97.9729 | 98.7835 | XGBoost | ensemble | K3B2 | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
8 | 100 | 30.978 | 39.016 | RandomForest | ensemble | K3B2 | KONS | Time
12 | 100 | 74.4384 | 67.2076 | RandomForest | ensemble | K3B2 | KONS | Time
14 | 100 | 82.8772 | 82.3514 | RandomForest | ensemble | K3B2 | KONS | Time
17 | 100 | 85.7422 | 85.3403 | RandomForest | ensemble | K3B2 | KONS | Time
20 | 100 | 91.5303 | 88.967 | RandomForest | ensemble | K3B2 | KONS | Time
25 | 100 | 97.9729 | 96.2735 | RandomForest | ensemble | K3B2 | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
8 | 100 | 30.978 | 199.0377 | Blending | ensemble | K3B2 | KONS | Time
12 | 100 | 74.4384 | 89.0142 | Blending | ensemble | K3B2 | KONS | Time
14 | 100 | 82.8772 | 77.658 | Blending | ensemble | K3B2 | KONS | Time
17 | 100 | 85.7422 | 82.3848 | Blending | ensemble | K3B2 | KONS | Time
20 | 100 | 91.5303 | 91.7554 | Blending | ensemble | K3B2 | KONS | Time
25 | 100 | 97.9729 | 96.8673 | Blending | ensemble | K3B2 | KONS | Time

## Kum
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.91316 | 11.331 | 5.9437 | XGBoost | ensemble | Kum | KONS | Time
6 | 1.4066 | 12.943 | 16.9062 | XGBoost | ensemble | Kum | KONS | Time
8 | 2.556 | 21.3793 | 25.49 | XGBoost | ensemble | Kum | KONS | Time
10 | 4.2312 | 32.7635 | 25.49 | XGBoost | ensemble | Kum | KONS | Time
11 | 5.0687 | 35.9859 | 37.0486 | XGBoost | ensemble | Kum | KONS | Time
17 | 22.678 | 42.0481 | 44.4777 | XGBoost | ensemble | Kum | KONS | Time
19 | 29.6475 | 46.8191 | 50.7936 | XGBoost | ensemble | Kum | KONS | Time
28 | 64.256 | 75.3868 | 77.8033 | XGBoost | ensemble | Kum | KONS | Time
41 | 100 | 96.067 | 95.9769 | XGBoost | ensemble | Kum | KONS | Time
42 | 100 | 96.067 | 96.4818 | XGBoost | ensemble | Kum | KONS | Time
54 | 100 | 99.5407 | 99.6885 | XGBoost | ensemble | Kum | KONS | Time
57 | 100 | 99.7333 | 99.6885 | XGBoost | ensemble | Kum | KONS | Time
58 | 100 | 99.8024 | 99.8916 | XGBoost | ensemble | Kum | KONS | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.91316 | 11.331 | 5.6052 | RandomForest | ensemble | Kum | KONS | Time
6 | 1.4066 | 12.943 | 13.4137 | RandomForest | ensemble | Kum | KONS | Time
8 | 2.556 | 21.3793 | 18.0643 | RandomForest | ensemble | Kum | KONS | Time
10 | 4.2312 | 32.7635 | 26.6028 | RandomForest | ensemble | Kum | KONS | Time
11 | 5.0687 | 35.9859 | 31.708 | RandomForest | ensemble | Kum | KONS | Time
17 | 22.678 | 42.0481 | 42.2243 | RandomForest | ensemble | Kum | KONS | Time
19 | 29.6475 | 46.8191 | 47.0454 | RandomForest | ensemble | Kum | KONS | Time
28 | 64.256 | 75.3868 | 73.3384 | RandomForest | ensemble | Kum | KONS | Time
41 | 100 | 96.067 | 95.8266 | RandomForest | ensemble | Kum | KONS | Time
42 | 100 | 96.067 | 96.3182 | RandomForest | ensemble | Kum | KONS | Time
54 | 100 | 99.5407 | 99.4508 | RandomForest | ensemble | Kum | KONS | Time
57 | 100 | 99.7333 | 99.7145 | RandomForest | ensemble | Kum | KONS | Time
58 | 100 | 99.8024 | 99.7268 | RandomForest | ensemble | Kum | KONS | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.91316 | 11.331 | -2.4558 | Blending | ensemble | Kum | KONS | Time
6 | 1.4066 | 12.943 | 0.33506 | Blending | ensemble | Kum | KONS | Time
8 | 2.556 | 21.3793 | 26.1845 | Blending | ensemble | Kum | KONS | Time
10 | 4.2312 | 32.7635 | 58.6225 | Blending | ensemble | Kum | KONS | Time
11 | 5.0687 | 35.9859 | 77.6756 | Blending | ensemble | Kum | KONS | Time
17 | 22.678 | 42.0481 | 34.5725 | Blending | ensemble | Kum | KONS | Time
19 | 29.6475 | 46.8191 | 38.9952 | Blending | ensemble | Kum | KONS | Time
28 | 64.256 | 75.3868 | 74.6868 | Blending | ensemble | Kum | KONS | Time
41 | 100 | 96.067 | 96.109 | Blending | ensemble | Kum | KONS | Time
42 | 100 | 96.067 | 96.3996 | Blending | ensemble | Kum | KONS | Time
54 | 100 | 99.5407 | 99.4917 | Blending | ensemble | Kum | KONS | Time
57 | 100 | 99.7333 | 99.7636 | Blending | ensemble | Kum | KONS | Time
58 | 100 | 99.8024 | 99.819 | Blending | ensemble | Kum | KONS | Time