## MK1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.55257 | 0.1756 | 0.17564 | XGBoost | ensemble | MK1 | MEP | Time
6 | 0.73676 | 0.1756 | 1.507 | XGBoost | ensemble | MK1 | MEP | Time
10 | 7.1775 | 25.5082 | 17.3286 | XGBoost | ensemble | MK1 | MEP | Time
11 | 8.7951 | 31.4701 | 32.137 | XGBoost | ensemble | MK1 | MEP | Time
16 | 18.8042 | 38.9161 | 38.2237 | XGBoost | ensemble | MK1 | MEP | Time
17 | 19.2224 | 44.9138 | 48.6192 | XGBoost | ensemble | MK1 | MEP | Time
42 | 74.5379 | 97.0039 | 97.0014 | XGBoost | ensemble | MK1 | MEP | Time
45 | 77.599 | 96.7389 | 96.8781 | XGBoost | ensemble | MK1 | MEP | Time
49 | 81.9815 | 97.1191 | 97.1156 | XGBoost | ensemble | MK1 | MEP | Time
55 | 92.927 | 97.531 | 97.5306 | XGBoost | ensemble | MK1 | MEP | Time
61 | 100 | 98.3356 | 98.4897 | XGBoost | ensemble | MK1 | MEP | Time
64 | 100 | 98.5726 | 98.5722 | XGBoost | ensemble | MK1 | MEP | Time
65 | 100 | 98.5726 | 98.5722 | XGBoost | ensemble | MK1 | MEP | Time
67 | 100 | 98.5726 | 99.6148 | XGBoost | ensemble | MK1 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.55257 | 0.1756 | 0.23736 | RandomForest | ensemble | MK1 | MEP | Time
6 | 0.73676 | 0.1756 | 0.8337 | RandomForest | ensemble | MK1 | MEP | Time
10 | 7.1775 | 25.5082 | 16.5015 | RandomForest | ensemble | MK1 | MEP | Time
11 | 8.7951 | 31.4701 | 26.3903 | RandomForest | ensemble | MK1 | MEP | Time
16 | 18.8042 | 38.9161 | 39.9354 | RandomForest | ensemble | MK1 | MEP | Time
17 | 19.2224 | 44.9138 | 46.2203 | RandomForest | ensemble | MK1 | MEP | Time
42 | 74.5379 | 97.0039 | 96.8435 | RandomForest | ensemble | MK1 | MEP | Time
45 | 77.599 | 96.7389 | 96.8902 | RandomForest | ensemble | MK1 | MEP | Time
49 | 81.9815 | 97.1191 | 97.0553 | RandomForest | ensemble | MK1 | MEP | Time
55 | 92.927 | 97.531 | 97.5356 | RandomForest | ensemble | MK1 | MEP | Time
61 | 100 | 98.3356 | 98.3322 | RandomForest | ensemble | MK1 | MEP | Time
64 | 100 | 98.5726 | 98.5504 | RandomForest | ensemble | MK1 | MEP | Time
65 | 100 | 98.5726 | 98.5987 | RandomForest | ensemble | MK1 | MEP | Time
67 | 100 | 98.5726 | 98.8954 | RandomForest | ensemble | MK1 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.55257 | 0.1756 | 2.9403 | Blending | ensemble | MK1 | MEP | Time
6 | 0.73676 | 0.1756 | 4.9048 | Blending | ensemble | MK1 | MEP | Time
10 | 7.1775 | 25.5082 | 18.0463 | Blending | ensemble | MK1 | MEP | Time
11 | 8.7951 | 31.4701 | 21.5587 | Blending | ensemble | MK1 | MEP | Time
16 | 18.8042 | 38.9161 | 40.8851 | Blending | ensemble | MK1 | MEP | Time
17 | 19.2224 | 44.9138 | 42.9046 | Blending | ensemble | MK1 | MEP | Time
42 | 74.5379 | 97.0039 | 96.8189 | Blending | ensemble | MK1 | MEP | Time
45 | 77.599 | 96.7389 | 96.6668 | Blending | ensemble | MK1 | MEP | Time
49 | 81.9815 | 97.1191 | 96.4234 | Blending | ensemble | MK1 | MEP | Time
55 | 92.927 | 97.531 | 97.52 | Blending | ensemble | MK1 | MEP | Time
61 | 100 | 98.3356 | 98.6298 | Blending | ensemble | MK1 | MEP | Time
64 | 100 | 98.5726 | 99.3682 | Blending | ensemble | MK1 | MEP | Time
65 | 100 | 98.5726 | 99.5808 | Blending | ensemble | MK1 | MEP | Time
67 | 100 | 98.5726 | 99.7107 | Blending | ensemble | MK1 | MEP | Time

## MK2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.62656 | 0.056249 | 0.056713 | XGBoost | ensemble | MK2 | MEP | Time
6 | 0.83541 | 0.056249 | 0.84958 | XGBoost | ensemble | MK2 | MEP | Time
10 | 7.2111 | 20.7776 | 13.3497 | XGBoost | ensemble | MK2 | MEP | Time
11 | 10.1724 | 25.0716 | 26.7118 | XGBoost | ensemble | MK2 | MEP | Time
16 | 28.4772 | 32.3222 | 31.9071 | XGBoost | ensemble | MK2 | MEP | Time
17 | 28.7758 | 38.8361 | 45.6006 | XGBoost | ensemble | MK2 | MEP | Time
42 | 64.4892 | 88.8693 | 88.872 | XGBoost | ensemble | MK2 | MEP | Time
45 | 73.0175 | 90.1135 | 91.1152 | XGBoost | ensemble | MK2 | MEP | Time
49 | 80.6177 | 94.1735 | 94.1746 | XGBoost | ensemble | MK2 | MEP | Time
55 | 93.9952 | 94.3742 | 95.6369 | XGBoost | ensemble | MK2 | MEP | Time
61 | 100 | 98.5973 | 98.5877 | XGBoost | ensemble | MK2 | MEP | Time
64 | 100 | 98.6973 | 98.6972 | XGBoost | ensemble | MK2 | MEP | Time
65 | 100 | 98.6973 | 98.6972 | XGBoost | ensemble | MK2 | MEP | Time
67 | 100 | 98.6973 | 99.9751 | XGBoost | ensemble | MK2 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.62656 | 0.056249 | 0.18137 | RandomForest | ensemble | MK2 | MEP | Time
6 | 0.83541 | 0.056249 | 0.64063 | RandomForest | ensemble | MK2 | MEP | Time
10 | 7.2111 | 20.7776 | 9.9359 | RandomForest | ensemble | MK2 | MEP | Time
11 | 10.1724 | 25.0716 | 22.673 | RandomForest | ensemble | MK2 | MEP | Time
16 | 28.4772 | 32.3222 | 37.3041 | RandomForest | ensemble | MK2 | MEP | Time
17 | 28.7758 | 38.8361 | 43.3312 | RandomForest | ensemble | MK2 | MEP | Time
42 | 64.4892 | 88.8693 | 88.0462 | RandomForest | ensemble | MK2 | MEP | Time
45 | 73.0175 | 90.1135 | 90.5912 | RandomForest | ensemble | MK2 | MEP | Time
49 | 80.6177 | 94.1735 | 93.8185 | RandomForest | ensemble | MK2 | MEP | Time
55 | 93.9952 | 94.3742 | 94.8568 | RandomForest | ensemble | MK2 | MEP | Time
61 | 100 | 98.5973 | 97.8438 | RandomForest | ensemble | MK2 | MEP | Time
64 | 100 | 98.6973 | 98.706 | RandomForest | ensemble | MK2 | MEP | Time
65 | 100 | 98.6973 | 98.755 | RandomForest | ensemble | MK2 | MEP | Time
67 | 100 | 98.6973 | 99.054 | RandomForest | ensemble | MK2 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.62656 | 0.056249 | 1.8193 | Blending | ensemble | MK2 | MEP | Time
6 | 0.83541 | 0.056249 | 3.0425 | Blending | ensemble | MK2 | MEP | Time
10 | 7.2111 | 20.7776 | 11.3523 | Blending | ensemble | MK2 | MEP | Time
11 | 10.1724 | 25.0716 | 16.0408 | Blending | ensemble | MK2 | MEP | Time
16 | 28.4772 | 32.3222 | 35.6677 | Blending | ensemble | MK2 | MEP | Time
17 | 28.7758 | 38.8361 | 39.1472 | Blending | ensemble | MK2 | MEP | Time
42 | 64.4892 | 88.8693 | 86.6659 | Blending | ensemble | MK2 | MEP | Time
45 | 73.0175 | 90.1135 | 92.0444 | Blending | ensemble | MK2 | MEP | Time
49 | 80.6177 | 94.1735 | 92.8896 | Blending | ensemble | MK2 | MEP | Time
55 | 93.9952 | 94.3742 | 95.6087 | Blending | ensemble | MK2 | MEP | Time
61 | 100 | 98.5973 | 98.9951 | Blending | ensemble | MK2 | MEP | Time
64 | 100 | 98.6973 | 99.1524 | Blending | ensemble | MK2 | MEP | Time
65 | 100 | 98.6973 | 99.3433 | Blending | ensemble | MK2 | MEP | Time
67 | 100 | 98.6973 | 99.6816 | Blending | ensemble | MK2 | MEP | Time

## EK1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 28.9528 | 0 | 0.0002209 | XGBoost | ensemble | EK1 | MEP | Time
8 | 31.5463 | 0 | 0.0002209 | XGBoost | ensemble | EK1 | MEP | Time
16 | 51.6706 | 0 | 0.0002209 | XGBoost | ensemble | EK1 | MEP | Time
17 | 54.1081 | 0.026255 | 0.025181 | XGBoost | ensemble | EK1 | MEP | Time
18 | 56.7785 | 0.026255 | 0.025181 | XGBoost | ensemble | EK1 | MEP | Time
21 | 65.0225 | 0.026255 | 0.023552 | XGBoost | ensemble | EK1 | MEP | Time
29 | 89.6521 | 2.4205 | 5.5672 | XGBoost | ensemble | EK1 | MEP | Time
32 | 97.8043 | 11.0154 | 11.0152 | XGBoost | ensemble | EK1 | MEP | Time
37 | 96.5562 | 19.5625 | 23.6955 | XGBoost | ensemble | EK1 | MEP | Time
41 | 96.2011 | 33.1626 | 26.4959 | XGBoost | ensemble | EK1 | MEP | Time
42 | 96.227 | 37.4792 | 42.997 | XGBoost | ensemble | EK1 | MEP | Time
44 | 96.2787 | 44.2091 | 45.7506 | XGBoost | ensemble | EK1 | MEP | Time
49 | 96.4081 | 52.3849 | 60.6113 | XGBoost | ensemble | EK1 | MEP | Time
58 | 98.4502 | 86.4012 | 86.4038 | XGBoost | ensemble | EK1 | MEP | Time
65 | 100 | 94.4302 | 94.4308 | XGBoost | ensemble | EK1 | MEP | Time
73 | 100 | 95.1073 | 95.5614 | XGBoost | ensemble | EK1 | MEP | Time
81 | 100 | 98.4556 | 98.7824 | XGBoost | ensemble | EK1 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 28.9528 | 0 | 0.00031051 | RandomForest | ensemble | EK1 | MEP | Time
8 | 31.5463 | 0 | 0.00031051 | RandomForest | ensemble | EK1 | MEP | Time
16 | 51.6706 | 0 | 0.00070434 | RandomForest | ensemble | EK1 | MEP | Time
17 | 54.1081 | 0.026255 | 0.0055912 | RandomForest | ensemble | EK1 | MEP | Time
18 | 56.7785 | 0.026255 | 0.02074 | RandomForest | ensemble | EK1 | MEP | Time
21 | 65.0225 | 0.026255 | 0.029199 | RandomForest | ensemble | EK1 | MEP | Time
29 | 89.6521 | 2.4205 | 2.439 | RandomForest | ensemble | EK1 | MEP | Time
32 | 97.8043 | 11.0154 | 11.5021 | RandomForest | ensemble | EK1 | MEP | Time
37 | 96.5562 | 19.5625 | 18.9897 | RandomForest | ensemble | EK1 | MEP | Time
41 | 96.2011 | 33.1626 | 28.3534 | RandomForest | ensemble | EK1 | MEP | Time
42 | 96.227 | 37.4792 | 36.9427 | RandomForest | ensemble | EK1 | MEP | Time
44 | 96.2787 | 44.2091 | 44.1626 | RandomForest | ensemble | EK1 | MEP | Time
49 | 96.4081 | 52.3849 | 52.9319 | RandomForest | ensemble | EK1 | MEP | Time
58 | 98.4502 | 86.4012 | 86.0354 | RandomForest | ensemble | EK1 | MEP | Time
65 | 100 | 94.4302 | 94.1303 | RandomForest | ensemble | EK1 | MEP | Time
73 | 100 | 95.1073 | 95.2623 | RandomForest | ensemble | EK1 | MEP | Time
81 | 100 | 98.4556 | 98.375 | RandomForest | ensemble | EK1 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
7 | 28.9528 | 0 | -6.6995 | Blending | ensemble | EK1 | MEP | Time
8 | 31.5463 | 0 | -12.1143 | Blending | ensemble | EK1 | MEP | Time
16 | 51.6706 | 0 | -28.4581 | Blending | ensemble | EK1 | MEP | Time
17 | 54.1081 | 0.026255 | -28.6088 | Blending | ensemble | EK1 | MEP | Time
18 | 56.7785 | 0.026255 | -28.1914 | Blending | ensemble | EK1 | MEP | Time
21 | 65.0225 | 0.026255 | -23.6106 | Blending | ensemble | EK1 | MEP | Time
29 | 89.6521 | 2.4205 | 3.1562 | Blending | ensemble | EK1 | MEP | Time
32 | 97.8043 | 11.0154 | -0.62218 | Blending | ensemble | EK1 | MEP | Time
37 | 96.5562 | 19.5625 | 23.0836 | Blending | ensemble | EK1 | MEP | Time
41 | 96.2011 | 33.1626 | 34.8347 | Blending | ensemble | EK1 | MEP | Time
42 | 96.227 | 37.4792 | 37.0906 | Blending | ensemble | EK1 | MEP | Time
44 | 96.2787 | 44.2091 | 41.6859 | Blending | ensemble | EK1 | MEP | Time
49 | 96.4081 | 52.3849 | 56.1658 | Blending | ensemble | EK1 | MEP | Time
58 | 98.4502 | 86.4012 | 90.0807 | Blending | ensemble | EK1 | MEP | Time
65 | 100 | 94.4302 | 92.75 | Blending | ensemble | EK1 | MEP | Time
73 | 100 | 95.1073 | 95.6291 | Blending | ensemble | EK1 | MEP | Time
81 | 100 | 98.4556 | 97.8847 | Blending | ensemble | EK1 | MEP | Time

## EK2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 42.201 | 0 | 0.00018883 | XGBoost | ensemble | EK2 | MEP | Time
8 | 45.4758 | 0 | 0.00018883 | XGBoost | ensemble | EK2 | MEP | Time
16 | 71.6746 | 0 | 0.00018883 | XGBoost | ensemble | EK2 | MEP | Time
17 | 74.9495 | 0.03363 | 0.033547 | XGBoost | ensemble | EK2 | MEP | Time
18 | 75.7646 | 0.03363 | 0.033547 | XGBoost | ensemble | EK2 | MEP | Time
21 | 78.4202 | 0.03363 | 0.033547 | XGBoost | ensemble | EK2 | MEP | Time
29 | 97.7249 | 3.1128 | 5.166 | XGBoost | ensemble | EK2 | MEP | Time
32 | 99.7702 | 9.1304 | 9.0559 | XGBoost | ensemble | EK2 | MEP | Time
37 | 96.6202 | 10.8314 | 12.7319 | XGBoost | ensemble | EK2 | MEP | Time
41 | 95.0021 | 16.8455 | 14.9047 | XGBoost | ensemble | EK2 | MEP | Time
42 | 94.7061 | 17.051 | 23.9646 | XGBoost | ensemble | EK2 | MEP | Time
44 | 94.1142 | 29.8334 | 29.8772 | XGBoost | ensemble | EK2 | MEP | Time
49 | 94.2452 | 35.3141 | 36.6268 | XGBoost | ensemble | EK2 | MEP | Time
58 | 98.6195 | 80.6004 | 80.4424 | XGBoost | ensemble | EK2 | MEP | Time
65 | 100 | 89.2971 | 89.296 | XGBoost | ensemble | EK2 | MEP | Time
73 | 100 | 91.9844 | 92.0435 | XGBoost | ensemble | EK2 | MEP | Time
81 | 100 | 99.2842 | 99.6927 | XGBoost | ensemble | EK2 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
7 | 42.201 | 0 | 0 | RandomForest | ensemble | EK2 | MEP | Time
8 | 45.4758 | 0 | 0 | RandomForest | ensemble | EK2 | MEP | Time
16 | 71.6746 | 0 | 0.007735 | RandomForest | ensemble | EK2 | MEP | Time
17 | 74.9495 | 0.03363 | 0.021355 | RandomForest | ensemble | EK2 | MEP | Time
18 | 75.7646 | 0.03363 | 0.029763 | RandomForest | ensemble | EK2 | MEP | Time
21 | 78.4202 | 0.03363 | 0.03458 | RandomForest | ensemble | EK2 | MEP | Time
29 | 97.7249 | 3.1128 | 3.1897 | RandomForest | ensemble | EK2 | MEP | Time
32 | 99.7702 | 9.1304 | 7.7038 | RandomForest | ensemble | EK2 | MEP | Time
37 | 96.6202 | 10.8314 | 9.9208 | RandomForest | ensemble | EK2 | MEP | Time
41 | 95.0021 | 16.8455 | 15.0507 | RandomForest | ensemble | EK2 | MEP | Time
42 | 94.7061 | 17.051 | 21.1337 | RandomForest | ensemble | EK2 | MEP | Time
44 | 94.1142 | 29.8334 | 27.4751 | RandomForest | ensemble | EK2 | MEP | Time
49 | 94.2452 | 35.3141 | 34.5737 | RandomForest | ensemble | EK2 | MEP | Time
58 | 98.6195 | 80.6004 | 78.9062 | RandomForest | ensemble | EK2 | MEP | Time
65 | 100 | 89.2971 | 88.271 | RandomForest | ensemble | EK2 | MEP | Time
73 | 100 | 91.9844 | 92.0206 | RandomForest | ensemble | EK2 | MEP | Time
81 | 100 | 99.2842 | 98.4901 | RandomForest | ensemble | EK2 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
7 | 42.201 | 0 | -34.6864 | Blending | ensemble | EK2 | MEP | Time
8 | 45.4758 | 0 | -28.5679 | Blending | ensemble | EK2 | MEP | Time
16 | 71.6746 | 0 | -20.3259 | Blending | ensemble | EK2 | MEP | Time
17 | 74.9495 | 0.03363 | -19.6971 | Blending | ensemble | EK2 | MEP | Time
18 | 75.7646 | 0.03363 | -16.5407 | Blending | ensemble | EK2 | MEP | Time
21 | 78.4202 | 0.03363 | -12.546 | Blending | ensemble | EK2 | MEP | Time
29 | 97.7249 | 3.1128 | 2.0691 | Blending | ensemble | EK2 | MEP | Time
32 | 99.7702 | 9.1304 | 3.3852 | Blending | ensemble | EK2 | MEP | Time
37 | 96.6202 | 10.8314 | 11.487 | Blending | ensemble | EK2 | MEP | Time
41 | 95.0021 | 16.8455 | 19.9011 | Blending | ensemble | EK2 | MEP | Time
42 | 94.7061 | 17.051 | 22.036 | Blending | ensemble | EK2 | MEP | Time
44 | 94.1142 | 29.8334 | 26.5923 | Blending | ensemble | EK2 | MEP | Time
49 | 94.2452 | 35.3141 | 37.2119 | Blending | ensemble | EK2 | MEP | Time
58 | 98.6195 | 80.6004 | 79.4462 | Blending | ensemble | EK2 | MEP | Time
65 | 100 | 89.2971 | 88.659 | Blending | ensemble | EK2 | MEP | Time
73 | 100 | 91.9844 | 92.1037 | Blending | ensemble | EK2 | MEP | Time
81 | 100 | 99.2842 | 98.822 | Blending | ensemble | EK2 | MEP | Time

## PB1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 7.7746 | 0 | 0.00029393 | XGBoost | ensemble | PB1 | MEP | Time
9 | 14.6805 | 0 | 0.00029393 | XGBoost | ensemble | PB1 | MEP | Time
16 | 23.7168 | 12.7545 | 12.7545 | XGBoost | ensemble | PB1 | MEP | Time
17 | 24.7167 | 6.9452 | 17.8668 | XGBoost | ensemble | PB1 | MEP | Time
18 | 25.8119 | 16.8699 | 17.8668 | XGBoost | ensemble | PB1 | MEP | Time
21 | 29.0976 | 19.1268 | 19.5074 | XGBoost | ensemble | PB1 | MEP | Time
29 | 42.4444 | 23.8265 | 26.8201 | XGBoost | ensemble | PB1 | MEP | Time
31 | 47.1447 | 27.2414 | 26.8201 | XGBoost | ensemble | PB1 | MEP | Time
32 | 48.371 | 30.3133 | 30.5143 | XGBoost | ensemble | PB1 | MEP | Time
41 | 61.1865 | 50.2184 | 50.8283 | XGBoost | ensemble | PB1 | MEP | Time
44 | 66.3329 | 53.7155 | 57.8989 | XGBoost | ensemble | PB1 | MEP | Time
46 | 69.7638 | 61.6612 | 66.5001 | XGBoost | ensemble | PB1 | MEP | Time
55 | 84.0438 | 83.0164 | 84.8948 | XGBoost | ensemble | PB1 | MEP | Time
61 | 93.3111 | 91.8576 | 92.5619 | XGBoost | ensemble | PB1 | MEP | Time
65 | 99.4894 | 93.2693 | 93.619 | XGBoost | ensemble | PB1 | MEP | Time
70 | 100 | 94.8188 | 94.9779 | XGBoost | ensemble | PB1 | MEP | Time
75 | 100 | 95.4235 | 95.3954 | XGBoost | ensemble | PB1 | MEP | Time
76 | 100 | 95.4235 | 95.4233 | XGBoost | ensemble | PB1 | MEP | Time
87 | 100 | 99.3915 | 99.477 | XGBoost | ensemble | PB1 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 7.7746 | 0 | 0.042786 | RandomForest | ensemble | PB1 | MEP | Time
9 | 14.6805 | 0 | 0.10427 | RandomForest | ensemble | PB1 | MEP | Time
16 | 23.7168 | 12.7545 | 12.2951 | RandomForest | ensemble | PB1 | MEP | Time
17 | 24.7167 | 6.9452 | 13.8498 | RandomForest | ensemble | PB1 | MEP | Time
18 | 25.8119 | 16.8699 | 18.0884 | RandomForest | ensemble | PB1 | MEP | Time
21 | 29.0976 | 19.1268 | 19.2866 | RandomForest | ensemble | PB1 | MEP | Time
29 | 42.4444 | 23.8265 | 24.7357 | RandomForest | ensemble | PB1 | MEP | Time
31 | 47.1447 | 27.2414 | 28.9686 | RandomForest | ensemble | PB1 | MEP | Time
32 | 48.371 | 30.3133 | 30.8768 | RandomForest | ensemble | PB1 | MEP | Time
41 | 61.1865 | 50.2184 | 48.9305 | RandomForest | ensemble | PB1 | MEP | Time
44 | 66.3329 | 53.7155 | 54.7465 | RandomForest | ensemble | PB1 | MEP | Time
46 | 69.7638 | 61.6612 | 65.6489 | RandomForest | ensemble | PB1 | MEP | Time
55 | 84.0438 | 83.0164 | 82.5045 | RandomForest | ensemble | PB1 | MEP | Time
61 | 93.3111 | 91.8576 | 91.9216 | RandomForest | ensemble | PB1 | MEP | Time
65 | 99.4894 | 93.2693 | 93.5137 | RandomForest | ensemble | PB1 | MEP | Time
70 | 100 | 94.8188 | 94.768 | RandomForest | ensemble | PB1 | MEP | Time
75 | 100 | 95.4235 | 95.108 | RandomForest | ensemble | PB1 | MEP | Time
76 | 100 | 95.4235 | 95.2849 | RandomForest | ensemble | PB1 | MEP | Time
87 | 100 | 99.3915 | 99.4659 | RandomForest | ensemble | PB1 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 7.7746 | 0 | 4.0897 | Blending | ensemble | PB1 | MEP | Time
9 | 14.6805 | 0 | 8.7662 | Blending | ensemble | PB1 | MEP | Time
16 | 23.7168 | 12.7545 | 13.7326 | Blending | ensemble | PB1 | MEP | Time
17 | 24.7167 | 6.9452 | 14.5475 | Blending | ensemble | PB1 | MEP | Time
18 | 25.8119 | 16.8699 | 15.3677 | Blending | ensemble | PB1 | MEP | Time
21 | 29.0976 | 19.1268 | 17.9613 | Blending | ensemble | PB1 | MEP | Time
29 | 42.4444 | 23.8265 | 25.9315 | Blending | ensemble | PB1 | MEP | Time
31 | 47.1447 | 27.2414 | 29.993 | Blending | ensemble | PB1 | MEP | Time
32 | 48.371 | 30.3133 | 31.4234 | Blending | ensemble | PB1 | MEP | Time
41 | 61.1865 | 50.2184 | 48.7399 | Blending | ensemble | PB1 | MEP | Time
44 | 66.3329 | 53.7155 | 57.4429 | Blending | ensemble | PB1 | MEP | Time
46 | 69.7638 | 61.6612 | 63.5978 | Blending | ensemble | PB1 | MEP | Time
55 | 84.0438 | 83.0164 | 86.2671 | Blending | ensemble | PB1 | MEP | Time
61 | 93.3111 | 91.8576 | 93.5755 | Blending | ensemble | PB1 | MEP | Time
65 | 99.4894 | 93.2693 | 92.1908 | Blending | ensemble | PB1 | MEP | Time
70 | 100 | 94.8188 | 94.733 | Blending | ensemble | PB1 | MEP | Time
75 | 100 | 95.4235 | 95.4136 | Blending | ensemble | PB1 | MEP | Time
76 | 100 | 95.4235 | 95.6097 | Blending | ensemble | PB1 | MEP | Time
87 | 100 | 99.3915 | 100.0144 | Blending | ensemble | PB1 | MEP | Time

## PB2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 8.9741 | 0 | 0.00025782 | XGBoost | ensemble | PB2 | MEP | Time
9 | 16.8533 | 0 | 0.00025782 | XGBoost | ensemble | PB2 | MEP | Time
16 | 28.3229 | 6.9833 | 6.9833 | XGBoost | ensemble | PB2 | MEP | Time
17 | 29.5197 | 3.0871 | 10.1933 | XGBoost | ensemble | PB2 | MEP | Time
18 | 30.8579 | 9.4289 | 10.1933 | XGBoost | ensemble | PB2 | MEP | Time
21 | 34.4477 | 10.5927 | 10.5897 | XGBoost | ensemble | PB2 | MEP | Time
29 | 41.4735 | 13.9403 | 16.0563 | XGBoost | ensemble | PB2 | MEP | Time
31 | 45.0099 | 16.3 | 16.0563 | XGBoost | ensemble | PB2 | MEP | Time
32 | 48.1217 | 17.1515 | 17.5676 | XGBoost | ensemble | PB2 | MEP | Time
41 | 65.4518 | 40.7966 | 42.777 | XGBoost | ensemble | PB2 | MEP | Time
44 | 69.5196 | 50.5001 | 53.4487 | XGBoost | ensemble | PB2 | MEP | Time
46 | 72.2315 | 54.7965 | 58.2574 | XGBoost | ensemble | PB2 | MEP | Time
55 | 84.4348 | 66.525 | 66.963 | XGBoost | ensemble | PB2 | MEP | Time
61 | 92.5704 | 72.6313 | 75.2031 | XGBoost | ensemble | PB2 | MEP | Time
65 | 98.6049 | 73.9678 | 79.348 | XGBoost | ensemble | PB2 | MEP | Time
70 | 99.0411 | 85.4853 | 86.536 | XGBoost | ensemble | PB2 | MEP | Time
75 | 99.4774 | 86.879 | 86.8768 | XGBoost | ensemble | PB2 | MEP | Time
76 | 99.5646 | 88.6505 | 88.6526 | XGBoost | ensemble | PB2 | MEP | Time
87 | 100 | 99.4412 | 99.4948 | XGBoost | ensemble | PB2 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 8.9741 | 0 | 0 | RandomForest | ensemble | PB2 | MEP | Time
9 | 16.8533 | 0 | 0 | RandomForest | ensemble | PB2 | MEP | Time
16 | 28.3229 | 6.9833 | 6.6394 | RandomForest | ensemble | PB2 | MEP | Time
17 | 29.5197 | 3.0871 | 7.5282 | RandomForest | ensemble | PB2 | MEP | Time
18 | 30.8579 | 9.4289 | 9.837 | RandomForest | ensemble | PB2 | MEP | Time
21 | 34.4477 | 10.5927 | 10.3978 | RandomForest | ensemble | PB2 | MEP | Time
29 | 41.4735 | 13.9403 | 13.2896 | RandomForest | ensemble | PB2 | MEP | Time
31 | 45.0099 | 16.3 | 15.5105 | RandomForest | ensemble | PB2 | MEP | Time
32 | 48.1217 | 17.1515 | 17.0725 | RandomForest | ensemble | PB2 | MEP | Time
41 | 65.4518 | 40.7966 | 39.7696 | RandomForest | ensemble | PB2 | MEP | Time
44 | 69.5196 | 50.5001 | 48.5154 | RandomForest | ensemble | PB2 | MEP | Time
46 | 72.2315 | 54.7965 | 55.0701 | RandomForest | ensemble | PB2 | MEP | Time
55 | 84.4348 | 66.525 | 65.6753 | RandomForest | ensemble | PB2 | MEP | Time
61 | 92.5704 | 72.6313 | 73.2086 | RandomForest | ensemble | PB2 | MEP | Time
65 | 98.6049 | 73.9678 | 77.8381 | RandomForest | ensemble | PB2 | MEP | Time
70 | 99.0411 | 85.4853 | 85.6264 | RandomForest | ensemble | PB2 | MEP | Time
75 | 99.4774 | 86.879 | 86.9971 | RandomForest | ensemble | PB2 | MEP | Time
76 | 99.5646 | 88.6505 | 87.7208 | RandomForest | ensemble | PB2 | MEP | Time
87 | 100 | 99.4412 | 99.4114 | RandomForest | ensemble | PB2 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 8.9741 | 0 | -0.4395 | Blending | ensemble | PB2 | MEP | Time
9 | 16.8533 | 0 | 1.4198 | Blending | ensemble | PB2 | MEP | Time
16 | 28.3229 | 6.9833 | 5.2826 | Blending | ensemble | PB2 | MEP | Time
17 | 29.5197 | 3.0871 | 5.8631 | Blending | ensemble | PB2 | MEP | Time
18 | 30.8579 | 9.4289 | 6.4133 | Blending | ensemble | PB2 | MEP | Time
21 | 34.4477 | 10.5927 | 8.6394 | Blending | ensemble | PB2 | MEP | Time
29 | 41.4735 | 13.9403 | 7.8168 | Blending | ensemble | PB2 | MEP | Time
31 | 45.0099 | 16.3 | 7.5376 | Blending | ensemble | PB2 | MEP | Time
32 | 48.1217 | 17.1515 | 13.9614 | Blending | ensemble | PB2 | MEP | Time
41 | 65.4518 | 40.7966 | 42.8894 | Blending | ensemble | PB2 | MEP | Time
44 | 69.5196 | 50.5001 | 49.8148 | Blending | ensemble | PB2 | MEP | Time
46 | 72.2315 | 54.7965 | 54.1039 | Blending | ensemble | PB2 | MEP | Time
55 | 84.4348 | 66.525 | 68.9406 | Blending | ensemble | PB2 | MEP | Time
61 | 92.5704 | 72.6313 | 73.9478 | Blending | ensemble | PB2 | MEP | Time
65 | 98.6049 | 73.9678 | 71.3454 | Blending | ensemble | PB2 | MEP | Time
70 | 99.0411 | 85.4853 | 85.6692 | Blending | ensemble | PB2 | MEP | Time
75 | 99.4774 | 86.879 | 85.7769 | Blending | ensemble | PB2 | MEP | Time
76 | 99.5646 | 88.6505 | 85.6516 | Blending | ensemble | PB2 | MEP | Time
87 | 100 | 99.4412 | 100.1628 | Blending | ensemble | PB2 | MEP | Time

## GKB1
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.86183 | 0 | 0.0003309 | XGBoost | ensemble | GKB1 | MEP | Time
9 | 4.3914 | 0 | 0.0003309 | XGBoost | ensemble | GKB1 | MEP | Time
16 | 11.615 | 1.2061 | 1.2061 | XGBoost | ensemble | GKB1 | MEP | Time
17 | 12.3603 | 0.65677 | 1.6896 | XGBoost | ensemble | GKB1 | MEP | Time
18 | 13.1161 | 1.5953 | 1.6896 | XGBoost | ensemble | GKB1 | MEP | Time
21 | 15.2692 | 1.8087 | 1.8447 | XGBoost | ensemble | GKB1 | MEP | Time
29 | 22.6792 | 3.1439 | 3.6433 | XGBoost | ensemble | GKB1 | MEP | Time
31 | 26.7868 | 12.4952 | 3.6433 | XGBoost | ensemble | GKB1 | MEP | Time
32 | 29.6846 | 17.4466 | 20.8673 | XGBoost | ensemble | GKB1 | MEP | Time
41 | 44.2068 | 38.648 | 40.8637 | XGBoost | ensemble | GKB1 | MEP | Time
44 | 50.9348 | 44.8516 | 47.0214 | XGBoost | ensemble | GKB1 | MEP | Time
46 | 58.2145 | 48.9574 | 53.4196 | XGBoost | ensemble | GKB1 | MEP | Time
55 | 72.8884 | 77.3316 | 79.9367 | XGBoost | ensemble | GKB1 | MEP | Time
61 | 80.2579 | 89.8902 | 90.9883 | XGBoost | ensemble | GKB1 | MEP | Time
65 | 83.8903 | 93.0816 | 93.6879 | XGBoost | ensemble | GKB1 | MEP | Time
70 | 87.535 | 95.8489 | 96.0118 | XGBoost | ensemble | GKB1 | MEP | Time
75 | 92.9577 | 96.2787 | 96.1445 | XGBoost | ensemble | GKB1 | MEP | Time
76 | 94.2622 | 96.5158 | 96.5185 | XGBoost | ensemble | GKB1 | MEP | Time
87 | 100 | 98.6107 | 98.7286 | XGBoost | ensemble | GKB1 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.86183 | 0 | 0 | RandomForest | ensemble | GKB1 | MEP | Time
9 | 4.3914 | 0 | 0.014217 | RandomForest | ensemble | GKB1 | MEP | Time
16 | 11.615 | 1.2061 | 1.2024 | RandomForest | ensemble | GKB1 | MEP | Time
17 | 12.3603 | 0.65677 | 1.4719 | RandomForest | ensemble | GKB1 | MEP | Time
18 | 13.1161 | 1.5953 | 1.675 | RandomForest | ensemble | GKB1 | MEP | Time
21 | 15.2692 | 1.8087 | 1.7687 | RandomForest | ensemble | GKB1 | MEP | Time
29 | 22.6792 | 3.1439 | 2.6178 | RandomForest | ensemble | GKB1 | MEP | Time
31 | 26.7868 | 12.4952 | 8.0995 | RandomForest | ensemble | GKB1 | MEP | Time
32 | 29.6846 | 17.4466 | 17.9767 | RandomForest | ensemble | GKB1 | MEP | Time
41 | 44.2068 | 38.648 | 36.774 | RandomForest | ensemble | GKB1 | MEP | Time
44 | 50.9348 | 44.8516 | 43.2524 | RandomForest | ensemble | GKB1 | MEP | Time
46 | 58.2145 | 48.9574 | 51.1503 | RandomForest | ensemble | GKB1 | MEP | Time
55 | 72.8884 | 77.3316 | 76.2439 | RandomForest | ensemble | GKB1 | MEP | Time
61 | 80.2579 | 89.8902 | 90.342 | RandomForest | ensemble | GKB1 | MEP | Time
65 | 83.8903 | 93.0816 | 93.3807 | RandomForest | ensemble | GKB1 | MEP | Time
70 | 87.535 | 95.8489 | 95.4014 | RandomForest | ensemble | GKB1 | MEP | Time
75 | 92.9577 | 96.2787 | 96.1867 | RandomForest | ensemble | GKB1 | MEP | Time
76 | 94.2622 | 96.5158 | 96.5182 | RandomForest | ensemble | GKB1 | MEP | Time
87 | 100 | 98.6107 | 98.5772 | RandomForest | ensemble | GKB1 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 0.86183 | 0 | 1.6782 | Blending | ensemble | GKB1 | MEP | Time
9 | 4.3914 | 0 | 0.49052 | Blending | ensemble | GKB1 | MEP | Time
16 | 11.615 | 1.2061 | 1.9358 | Blending | ensemble | GKB1 | MEP | Time
17 | 12.3603 | 0.65677 | 2.5299 | Blending | ensemble | GKB1 | MEP | Time
18 | 13.1161 | 1.5953 | 3.0243 | Blending | ensemble | GKB1 | MEP | Time
21 | 15.2692 | 1.8087 | 3.4869 | Blending | ensemble | GKB1 | MEP | Time
29 | 22.6792 | 3.1439 | 2.0556 | Blending | ensemble | GKB1 | MEP | Time
31 | 26.7868 | 12.4952 | 10.7647 | Blending | ensemble | GKB1 | MEP | Time
32 | 29.6846 | 17.4466 | 16.5669 | Blending | ensemble | GKB1 | MEP | Time
41 | 44.2068 | 38.648 | 36.1837 | Blending | ensemble | GKB1 | MEP | Time
44 | 50.9348 | 44.8516 | 44.8196 | Blending | ensemble | GKB1 | MEP | Time
46 | 58.2145 | 48.9574 | 50.8075 | Blending | ensemble | GKB1 | MEP | Time
55 | 72.8884 | 77.3316 | 78.1378 | Blending | ensemble | GKB1 | MEP | Time
61 | 80.2579 | 89.8902 | 90.2179 | Blending | ensemble | GKB1 | MEP | Time
65 | 83.8903 | 93.0816 | 93.8571 | Blending | ensemble | GKB1 | MEP | Time
70 | 87.535 | 95.8489 | 95.263 | Blending | ensemble | GKB1 | MEP | Time
75 | 92.9577 | 96.2787 | 97.0791 | Blending | ensemble | GKB1 | MEP | Time
76 | 94.2622 | 96.5158 | 97.3469 | Blending | ensemble | GKB1 | MEP | Time
87 | 100 | 98.6107 | 98.125 | Blending | ensemble | GKB1 | MEP | Time

## GKB2
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 1.3977 | 0 | 0.00025878 | XGBoost | ensemble | GKB2 | MEP | Time
9 | 7.1226 | 0 | 0.00025878 | XGBoost | ensemble | GKB2 | MEP | Time
16 | 17.9558 | 1.0582 | 1.0583 | XGBoost | ensemble | GKB2 | MEP | Time
17 | 18.9948 | 0.46782 | 1.5433 | XGBoost | ensemble | GKB2 | MEP | Time
18 | 20.0558 | 1.4288 | 1.5433 | XGBoost | ensemble | GKB2 | MEP | Time
21 | 23.1727 | 1.6052 | 1.6053 | XGBoost | ensemble | GKB2 | MEP | Time
29 | 29.204 | 2.5836 | 2.9932 | XGBoost | ensemble | GKB2 | MEP | Time
31 | 33.871 | 9.7545 | 2.9932 | XGBoost | ensemble | GKB2 | MEP | Time
32 | 36.3204 | 13.9128 | 16.308 | XGBoost | ensemble | GKB2 | MEP | Time
41 | 52.7667 | 34.0137 | 36.4152 | XGBoost | ensemble | GKB2 | MEP | Time
44 | 55.3322 | 40.0497 | 41.3476 | XGBoost | ensemble | GKB2 | MEP | Time
46 | 55.8925 | 42.9757 | 45.8072 | XGBoost | ensemble | GKB2 | MEP | Time
55 | 62.8074 | 64.408 | 65.8465 | XGBoost | ensemble | GKB2 | MEP | Time
61 | 71.0189 | 77.3577 | 79.8401 | XGBoost | ensemble | GKB2 | MEP | Time
65 | 80.5728 | 84.0807 | 86.5568 | XGBoost | ensemble | GKB2 | MEP | Time
70 | 87.4238 | 90.8444 | 91.5238 | XGBoost | ensemble | GKB2 | MEP | Time
75 | 93.7806 | 92.055 | 91.9676 | XGBoost | ensemble | GKB2 | MEP | Time
76 | 95.3165 | 92.6107 | 92.7776 | XGBoost | ensemble | GKB2 | MEP | Time
87 | 100 | 98.9896 | 99.1227 | XGBoost | ensemble | GKB2 | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 1.3977 | 0 | 0 | RandomForest | ensemble | GKB2 | MEP | Time
9 | 7.1226 | 0 | 0.012728 | RandomForest | ensemble | GKB2 | MEP | Time
16 | 17.9558 | 1.0582 | 0.99655 | RandomForest | ensemble | GKB2 | MEP | Time
17 | 18.9948 | 0.46782 | 1.2067 | RandomForest | ensemble | GKB2 | MEP | Time
18 | 20.0558 | 1.4288 | 1.5841 | RandomForest | ensemble | GKB2 | MEP | Time
21 | 23.1727 | 1.6052 | 1.6668 | RandomForest | ensemble | GKB2 | MEP | Time
29 | 29.204 | 2.5836 | 2.0823 | RandomForest | ensemble | GKB2 | MEP | Time
31 | 33.871 | 9.7545 | 8.6392 | RandomForest | ensemble | GKB2 | MEP | Time
32 | 36.3204 | 13.9128 | 13.7268 | RandomForest | ensemble | GKB2 | MEP | Time
41 | 52.7667 | 34.0137 | 33.5902 | RandomForest | ensemble | GKB2 | MEP | Time
44 | 55.3322 | 40.0497 | 39.1569 | RandomForest | ensemble | GKB2 | MEP | Time
46 | 55.8925 | 42.9757 | 42.9941 | RandomForest | ensemble | GKB2 | MEP | Time
55 | 62.8074 | 64.408 | 63.6125 | RandomForest | ensemble | GKB2 | MEP | Time
61 | 71.0189 | 77.3577 | 75.1988 | RandomForest | ensemble | GKB2 | MEP | Time
65 | 80.5728 | 84.0807 | 85.5544 | RandomForest | ensemble | GKB2 | MEP | Time
70 | 87.4238 | 90.8444 | 90.4201 | RandomForest | ensemble | GKB2 | MEP | Time
75 | 93.7806 | 92.055 | 92.0202 | RandomForest | ensemble | GKB2 | MEP | Time
76 | 95.3165 | 92.6107 | 92.6314 | RandomForest | ensemble | GKB2 | MEP | Time
87 | 100 | 98.9896 | 98.7795 | RandomForest | ensemble | GKB2 | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 1.3977 | 0 | 3.9945 | Blending | ensemble | GKB2 | MEP | Time
9 | 7.1226 | 0 | 2.6925 | Blending | ensemble | GKB2 | MEP | Time
16 | 17.9558 | 1.0582 | 0.5178 | Blending | ensemble | GKB2 | MEP | Time
17 | 18.9948 | 0.46782 | 1.1064 | Blending | ensemble | GKB2 | MEP | Time
18 | 20.0558 | 1.4288 | 1.6858 | Blending | ensemble | GKB2 | MEP | Time
21 | 23.1727 | 1.6052 | 3.5985 | Blending | ensemble | GKB2 | MEP | Time
29 | 29.204 | 2.5836 | -0.89233 | Blending | ensemble | GKB2 | MEP | Time
31 | 33.871 | 9.7545 | 12.52 | Blending | ensemble | GKB2 | MEP | Time
32 | 36.3204 | 13.9128 | 16.3241 | Blending | ensemble | GKB2 | MEP | Time
41 | 52.7667 | 34.0137 | 33.0632 | Blending | ensemble | GKB2 | MEP | Time
44 | 55.3322 | 40.0497 | 40.4846 | Blending | ensemble | GKB2 | MEP | Time
46 | 55.8925 | 42.9757 | 46.0159 | Blending | ensemble | GKB2 | MEP | Time
55 | 62.8074 | 64.408 | 65.7248 | Blending | ensemble | GKB2 | MEP | Time
61 | 71.0189 | 77.3577 | 80.3566 | Blending | ensemble | GKB2 | MEP | Time
65 | 80.5728 | 84.0807 | 84.1435 | Blending | ensemble | GKB2 | MEP | Time
70 | 87.4238 | 90.8444 | 90.1191 | Blending | ensemble | GKB2 | MEP | Time
75 | 93.7806 | 92.055 | 93.127 | Blending | ensemble | GKB2 | MEP | Time
76 | 95.3165 | 92.6107 | 93.1287 | Blending | ensemble | GKB2 | MEP | Time
87 | 100 | 98.9896 | 100.6996 | Blending | ensemble | GKB2 | MEP | Time

## GKB
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 1.1268 | 0 | 0.00030925 | XGBoost | ensemble | GKB | MEP | Time
9 | 5.7419 | 0 | 0.00030925 | XGBoost | ensemble | GKB | MEP | Time
16 | 14.7503 | 1.1305 | 1.1305 | XGBoost | ensemble | GKB | MEP | Time
17 | 15.6408 | 0.56011 | 1.6158 | XGBoost | ensemble | GKB | MEP | Time
18 | 16.5476 | 1.5101 | 1.6158 | XGBoost | ensemble | GKB | MEP | Time
21 | 19.1772 | 1.7046 | 1.7223 | XGBoost | ensemble | GKB | MEP | Time
29 | 25.9055 | 2.8573 | 3.3108 | XGBoost | ensemble | GKB | MEP | Time
31 | 30.2897 | 11.0932 | 3.3108 | XGBoost | ensemble | GKB | MEP | Time
32 | 32.9658 | 15.6389 | 18.5332 | XGBoost | ensemble | GKB | MEP | Time
41 | 48.4394 | 36.2773 | 38.5969 | XGBoost | ensemble | GKB | MEP | Time
44 | 53.1091 | 42.3952 | 44.1159 | XGBoost | ensemble | GKB | MEP | Time
46 | 57.0663 | 45.8974 | 49.527 | XGBoost | ensemble | GKB | MEP | Time
55 | 67.9037 | 70.7205 | 72.7278 | XGBoost | ensemble | GKB | MEP | Time
61 | 75.6895 | 83.4792 | 85.2783 | XGBoost | ensemble | GKB | MEP | Time
65 | 82.2499 | 88.4772 | 90.0392 | XGBoost | ensemble | GKB | MEP | Time
70 | 87.48 | 93.2888 | 93.7158 | XGBoost | ensemble | GKB | MEP | Time
75 | 93.3646 | 94.118 | 94.0149 | XGBoost | ensemble | GKB | MEP | Time
76 | 94.7835 | 94.5182 | 94.5984 | XGBoost | ensemble | GKB | MEP | Time
87 | 100 | 98.8045 | 98.9302 | XGBoost | ensemble | GKB | MEP | Time
AT | Planned Value | Actual | EV_Pred | Model | Method | Subwork | Work | Process
5 | 1.1268 | 0 | 0 | RandomForest | ensemble | GKB | MEP | Time
9 | 5.7419 | 0 | 0 | RandomForest | ensemble | GKB | MEP | Time
16 | 14.7503 | 1.1305 | 1.1168 | RandomForest | ensemble | GKB | MEP | Time
17 | 15.6408 | 0.56011 | 1.2561 | RandomForest | ensemble | GKB | MEP | Time
18 | 16.5476 | 1.5101 | 1.5534 | RandomForest | ensemble | GKB | MEP | Time
21 | 19.1772 | 1.7046 | 1.6951 | RandomForest | ensemble | GKB | MEP | Time
29 | 25.9055 | 2.8573 | 2.4114 | RandomForest | ensemble | GKB | MEP | Time
31 | 30.2897 | 11.0932 | 6.5193 | RandomForest | ensemble | GKB | MEP | Time
32 | 32.9658 | 15.6389 | 15.2817 | RandomForest | ensemble | GKB | MEP | Time
41 | 48.4394 | 36.2773 | 34.933 | RandomForest | ensemble | GKB | MEP | Time
44 | 53.1091 | 42.3952 | 41.1339 | RandomForest | ensemble | GKB | MEP | Time
46 | 57.0663 | 45.8974 | 47.5919 | RandomForest | ensemble | GKB | MEP | Time
55 | 67.9037 | 70.7205 | 69.9434 | RandomForest | ensemble | GKB | MEP | Time
61 | 75.6895 | 83.4792 | 82.6617 | RandomForest | ensemble | GKB | MEP | Time
65 | 82.2499 | 88.4772 | 89.2013 | RandomForest | ensemble | GKB | MEP | Time
70 | 87.48 | 93.2888 | 92.6856 | RandomForest | ensemble | GKB | MEP | Time
75 | 93.3646 | 94.118 | 94.1171 | RandomForest | ensemble | GKB | MEP | Time
76 | 94.7835 | 94.5182 | 94.5376 | RandomForest | ensemble | GKB | MEP | Time
87 | 100 | 98.8045 | 98.6153 | RandomForest | ensemble | GKB | MEP | Time
Minggu | Planned Value | Earned Value | EV_Pred | Model | Method | Subwork | Work | Process
5 | 1.1268 | 0 | -9.4332 | Blending | ensemble | GKB | MEP | Time
9 | 5.7419 | 0 | -6.9405 | Blending | ensemble | GKB | MEP | Time
16 | 14.7503 | 1.1305 | 0.23034 | Blending | ensemble | GKB | MEP | Time
17 | 15.6408 | 0.56011 | 0.19056 | Blending | ensemble | GKB | MEP | Time
18 | 16.5476 | 1.5101 | 0.26952 | Blending | ensemble | GKB | MEP | Time
21 | 19.1772 | 1.7046 | 0.7742 | Blending | ensemble | GKB | MEP | Time
29 | 25.9055 | 2.8573 | 6.2276 | Blending | ensemble | GKB | MEP | Time
31 | 30.2897 | 11.0932 | 11.1289 | Blending | ensemble | GKB | MEP | Time
32 | 32.9658 | 15.6389 | 14.5914 | Blending | ensemble | GKB | MEP | Time
41 | 48.4394 | 36.2773 | 35.5569 | Blending | ensemble | GKB | MEP | Time
44 | 53.1091 | 42.3952 | 42.989 | Blending | ensemble | GKB | MEP | Time
46 | 57.0663 | 45.8974 | 49.3033 | Blending | ensemble | GKB | MEP | Time
55 | 67.9037 | 70.7205 | 68.3549 | Blending | ensemble | GKB | MEP | Time
61 | 75.6895 | 83.4792 | 80.0132 | Blending | ensemble | GKB | MEP | Time
65 | 82.2499 | 88.4772 | 90.3419 | Blending | ensemble | GKB | MEP | Time
70 | 87.48 | 93.2888 | 93.1633 | Blending | ensemble | GKB | MEP | Time
75 | 93.3646 | 94.118 | 95.2278 | Blending | ensemble | GKB | MEP | Time
76 | 94.7835 | 94.5182 | 95.2085 | Blending | ensemble | GKB | MEP | Time
87 | 100 | 98.8045 | 98.7259 | Blending | ensemble | GKB | MEP | Time